## Staff
2020 CSTE Annual Conference Program Planning Timeline - STAFF
Schedule | Email | Activities | Roles
June - September |  | Apply with CDC for 2020 CE Credits | Jessica A.
June - August |  | Initial 2020 AC Website | IT / Beverly / Communications
August/ September |  | Select Site for 2022 conference | Beverly / ED / President Elect
August / September |  | Identify and develop workshops (Senior Management will identify space and funding / Program/Workforce Staff will execute development; Program will submit list of proposed workshops from CoAg as starting point) - WORKSHOPS have to be developed early if Staff want information in Confex by October | Senior Management / Program/Workforce Staff
August 23 |  | Committee and staff assignments finalized for Confex programming | Dhara
August 23 |  | IT update EB elections process with new dates; Review voting process | IT / Beverly / ED
September EB Meeting |  | Obtain Planning Committee CE Form | Jessica A.
September 3 - 19 |  | Program staff working with committees to develop topics for abstract process | Program Staff
DEADLINE – September 20 |  | Deadline for Submission of Topics (hard deadline in CONFEX) | Program Staff
DEADLINE – September 20 |  | Any new Confex Report Needs Identified in Detail by Program/Workforce staff and submitted to Beverly | Program/Workforce Staff/ Beverly
October - December |  | Sponsored travel planning (database needs, letters, emails, etc.) | IT / Accounting / Mone' / Dhara / Jennifer / Valerie
DEADLINE – October 1 |  | Finalize Position Statement Office Open Hours for website, Confex programming and agenda | Program Staff
October 1 - 10 |  | Staff abstract submission testing, provide feedback on an ongoing basis | Program Staff
DEADLINE – October 10 |  | Staff abstract submissions testing completed in CONFEX (no test submissions after this date) | Program/Workforce Staff
October 15 | x | Announce sponsor / exhibitor opportunities | Jeremy / Beverly
November 1 | x | Open Call for Abstracts | Beverly / IT
November 1 |  | Managers submit number of staff traveling for the AC to Beverly for staff block hold; Workforce staff submit number of fellow and student scholarship rooms; Staff will make their own reservations through Passkey for AC and vacation arrangements on their own | Senior Management
DEADLINE – November 15 |  | Enter breakout session allocations in CONFEX based on evaluation data, room counts, space limitation, and topics/needs of Sub-Committees | Beverly
November - December |  | App vendor request for bids and review | Clay / Beverly
December |  | Program team meetings to review Confex abstract review and session building | Beverly / Program Staff
December | x | Announce Position Statement Process | Meredith / Dhara / IT
December 2 - January 13 |  | CDC travelers for workshops and invited meetings identified | Program/Workforce Staff
December 2 - January 17 |  | Program staff and Admins begin process of identifying sponsored travelers | Program Staff / Mone' / Admins
DEADLINE – December 6 |  | ALL workshops FINALIZED Main Subject Titles for Registration Process; i.e.. Zika, HAI, MCH (hard deadline); include meeting room set requirements (classroom, rounds, etc.) from discussions with workshop member leads and program management; Subtitles with more descriptive language due in January; INCLUDE preferred final room seating and estimated seating requirements; seating may be changed based on overall AC needs; Confirmation of waitlist options | Program/Workforce Staff / IT / Beverly
DEADLINE – December 6 |  | Sponsored travel planning (database needs, letters, emails, etc.) - FINAL form requirements, including registration, emails and letters to Kevin | IT / Accounting / Mone' / Dhara / Jennifer / Valerie
DEADLINE – December 6 |  | Any credit card processing requirements set-up and ready for registration opening; including tax issues/waivers for state. | John / Shelia
DEADLINE – December 6 |  | Run (or fitness activity) planning and t-shirt pricing finalized | Communications & TBD Program Staff or Support Services Staff
DEADLINE – December 6 |  | CE forms, examples, and share spreadsheet for plenary and workshop speaker forms. | TBD Workforce Staff
DEADLINE – December 6 |  | Establish budget for student scholarships and number of recipients | John / Amanda
December 6 |  | Confirm process for sponsors and exhibitors to register | IT / Beverly / Communications
January |  | Confirm Speaker for Jonathan Mann Lecturer | President-Elect / Executive Board
January |  | Confirm Plenary Speakers | President Elect / Beverly
January / February |  | Planning for lapel pin design and voting | Beverly / Kevin / Shundra
DEADLINE – January 10 | x | Deadline for Submission of Abstracts (hard deadline in Confex)
DEADLINE – January 13 |  | Deadline for CDC personnel required at workshops from staff submitted | Program/Workforce
DEADLINE – January 13 |  | Final t-shirt design for registration process | Communications / Kevin / Jennifer
DEADLINE – January 13 |  | ALL workshops descriptions FINALIZED for registration opening (Titles finalized back in December, Subtitles added at this point); | Program/Workforce Staff
January 13 |  | Internal review of incomplete abstracts | Beverly
January 14-16 |  | Program staff conduct an internal review of submitted abstracts | Program Staff
DEADLINE – January 16 | x | Open call for EB nominations | IT / Membership
DEADLINE – January 17 |  | Internal transfer and reassignment of abstracts completed between committees (step 1) | Program Staff
DEADLINE – January 17 |  | IT finalized travel database needs and letters in system | Kevin
DEADLINE – January 17 |  | Deadline for Program/Workforce staff to finalize list of sponsored travelers and send to Admins; Purchase orders submitted | Program/Workforce Staff
January 18-25 |  | Admins enter final list of sponsored travelers in database (any lists after this deadline must be entered by program staff) | Admins
DEADLINE - January 21 |  | Reviewers assigned to topics (step 2) and send REVIEW Communications | Program Staff
January 23 | x | Announce awards | Beverly / ED / Communications
DEADLINE – January 24 |  | Review registration website for testing | IT
DEADLINE – January 24 |  | Sponsor final payments and logos | Communications
DEADLINE – January 24 |  | Review AC website pages for registration opening | IT
DEADLINE – January 27 |  | Sponsored Traveler list to Program/Workforce Staff for Review | Kevin
January 28-31 |  | Admins and program staff review travelers in database in preparation for registration opening | Admins/Program/Workforce
DEADLINE – January 29 |  | Deadline for all AC website and registration pages finalized from review | IT
January 30 | x | Announce student scholarship opportunities | Workforce / John
January 31 | x | State Epi travel letter to AC | Tarajee / ED / Communications
February / March |  | App Planning | Clay / Beverly
DEADLINE – February 5 |  | Abstract review by external reviewers (hard deadline in Confex) | Sub-Committees / Program Staff
February 5 | x | Open Registration and Hotel Accommodations (EB requested afternoon opening for all due to time difference in Alaska & Hawaii) | IT / Beverly
February 5 |  | Sponsored travelers notified of support | Program Staff / Mone' / IT
February 5 |  | Retired Past Presidents notified of support | Shundra
February 6 |  | Program sub-committee conference calls begin | Sub-Committees / Program Staff
DEADLINE – February 13 | x | Deadline for EB nominations | IT / Membership
February 19 |  | Registration Parked Reports uploaded to Basecamp | Kevin / Brett
February 19 |  | Develop and solicit RFP for photographer | Communications / Beverly
DEADLINE – February 19 |  | Last day for sub-committee abstract review and program planning conference calls | Sub-Committees / Program Staff
DEADLINE – February 19 |  | Room types for oral presentations (breakout, quick, lightning) provided to Beverly for Confex programming. AND, transfer of any sessions to another committee. NOTE: Session building can not start until room types are updated in Confex by Beverly (allow time for programming) | Program Staff
February 19 – March 11 |  | Program staff finalize sessions and abstract determinations | Program Staff
DEADLINE – February 20 |  | EB Nominee questionnaire distributed | Beverly
March |  | Finalize and order name badges | Beverly / Clay
March 2 | x | Deadline for Award nominations | Beverly / ED / Amanda
DEADLINE – March 2 |  | Student Scholarship application submission | Workforce
DEADLINE – March 5 |  | Deadline for EB Nominee questionnaire form completed | Beverly
March/April EB Conference Call |  | Finalize Award Recipients & Slate of Candidates | Executive Board
DEADLINE – March 6 |  | Deadline for plenary and workshop speaker CE forms | TBD Workforce Staff
March 6 |  | Finalize non-abstract roundtable sessions (Emily, Mentor breakfast, Fellow lunch, invited sessions, etc. ) | Communications / Workforce
DEADLINE – March 11 HARD DEADLINE for ALL committees entered into CONFEX |  | Program staff confirm all sessions and abstract determinations in database for speaker invitations, including moderators and poster finalists and session titles - ANY CHANGES after this date communicated to Beverly, do not enter in Confex | Program Staff / Beverly
DEADLINE – March 12-13 |  | Identify and resolve any speaker/moderator conflicts (updates in Confex will be made by Beverly) | Beverly / Program Staff
Week of March 23 |  | Student Scholarship recipient(s) notified of support | Workforce
DEADLINE – March 27 |  | RWJF finalists identified for program (entrees saved in registration system) | Cailyn / Shundra
DEADLINE – March 27 | x | Speaker letters of Invitation and Declined Abstracts Sent (Declined oral presentations should be addressed by program staff within 1 week of receipt) | Beverly / Kevin
April |  | Planning for presenting author reminder communications (distribution dates determined at this point) | Beverly / IT / Communications
April |  | Finalize arrangements and service order for CSTE Exhibit Booth; Start planning and production timeline for program/workforce materials and one-pagers | Communications / Dhara / Amanda
April 1 |  | Review list of exhibitor / sponsor payments and registration | Communications / Shelia / Beverly
April 1 |  | Finalized exhibitor and sponsor information for pocket agenda | Communications
DEADLINE – April 1 |  | Workshop start and end times REQUIRED for pocket agenda printing | Program/Workforce Staff
DEADLINE – April 1 |  | Hard Deadline for any final changes to AV, IT, any Equipment or Internet needs for workshops (includes any CSTE equipment where connectivity to AV is required; i.e. CatchBox mics). Breakouts and roundtables have standard sets to max capacity. Workshop evaluation needs coordinated through evaluation team. | Program/Workforce / Evaluations / Beverly
DEADLINE – April 1 |  | RWJF finalists registered and final entrée selection saved; and deadline for RWJF document information (pictures, abstracts, bios) | Cailyn / Shundra
DEADLINE – April 1 |  | Final evaluation template prepared | Evaluation
DEADLINE – April 1 |  | Finalize equipment needs with Confex | Beverly / IT
DEADLINE – April 2 |  | Ordinary Process Position Statements Due to CSTE | Program Staff / IT
April 3 | x | Open Late-Breaker Abstract Process | Beverly / IT
Week of April 13 | x | Send sponsored travelers reminder email for registration and travel | Program Staff / IT / Mone' / Communications
DEADLINE – April 15 |  | Confirm student scholarship travel and registration | Workforce
DEADLINE – April 15 |  | Talking points and speeches for President-Elect, President & ED (fellowship graduation ceremony, opening plenary, banquet, state of CSTE) | Communications
DEADLINE – April 15 |  | Finalize agenda feeds and information for App | Beverly / IT
DEADLINE – April 16 | x | Announce candidate slate to Active members | ED / Communications / Beverly / IT
DEADLINE – April 17 | x | Deadline for Submission of Late Breaker Abstracts | Beverly
DEADLINE – April 17 |  | Daily Glance Agendas posted to Website | Beverly / IT
DEADLINE – April 23 |  | Deadline for CE application package | TBD Workforce Staff
May / June |  | Apply 2021 AC CE credits so critical dates are identified early | Jessica A.
DEADLINE – May 1 |  | Late-Breaker Agenda Finalized | President-Elect / Beverly
DEADLINE – May 1 |  | Communications submit final edited proofs of any program/workforce documents | Communications / Dhara / Amanda
DEADLINE – May 4 |  | Deadline for Active Member eligibility to vote in elections | IT / Membership
May 6 |  | Late-Breaker invitation (and decline) letters sent | Beverly / IT
DEADLINE – May 7 | x | Open EB voting for Active Members | IT / Membership / Communications / ED
DEADLINE – May 7 |  | Tellers confirmed EB voting | Beverly / ED / Kevin
May 7 |  | Review AC at Staff Meeting | Beverly
Week of May 11 | x | Send sponsored travelers reminder email for registration and travel | Program Staff / IT / Mone' / Communications
DEADLINE – May 13 | x | Early-Bird Registration | Operations / Accounting
DEADLINE – May 13 |  | Speaker response to invitation
May 15 |  | Submit F&B to Hotel / Convention Center | Beverly
May 15 |  | Order promotional items, tote bags, AC pins and ribbons | Communications / Shundra
May 15 |  | Finalized t-shirt order and provide counts by shirt size for registration limits | Jennifer
DEADLINE – May 21 | x | Deadline for EB voting | IT / Membership
DEADLINE – May 21 | x | Post Ordinary Process Position Statements on Website | Meredith / Dhara / IT / Communications
DEADLINE – May 28 | x | Open run-off/secondary elections for Active members or if no run off elections then announcement to membership | IT / Membership / Communications / ED
DEADLINE – May 28 |  | Deadline for pertinent speaker changes CE forms | Jessica A
DEADLINE – May 29 |  | Deadline for PDF Sunday agendas for online program and app | Program/Workforce
Week of June 1 | x | App announced to attendees | Beverly / IT
DEADLINE – June 3 |  | All Conference Materials Packed, Identified on Load List and Ready for Shipment on AV truck (Tentative as of July 2019 and final date TBD) | National Office
DEADLINE – June 11 | x | Deadline for run-off/secondary elections | IT / Membership
DEADLINE – June 11 |  | Expedited Process Position Statements Due to CSTE | Program Staff / IT
DEADLINE – June 12 | x | Advanced deadline for presentation upload in Confex
DEADLINE – June 12 |  | Close workshops and waitlists at capacity; Program staff communicate to non-accepted waitlist folks | Program / Registration
DEADLINE – June 12 |  | Review sponsored travelers and Sunday speakers not registered and provide a list for registration desk to confirm access to Sunday session | Program/Workforce
DEADLINE – June 18 | x | Post Expedited Position Statements on Website | Meredith / Dhara / IT
Week of June 15 | x | Announce new Executive Board (if run off elections) | ED / Communications / Beverly / IT
Week of June 22 | x | Before you arrive Email | Communications / IT
Week of June 22 | x | Send reimbursement forms to sponsored travelers | Program Staff / IT / Accounting / Mone'
June 25 |  | Operations support staff travel | Operations / Accounting
JUNE 28 - JULY 2 |  | ANNUAL CONFERENCE | Staff attending AC
July 2 |  | Update EB on website (multiple locations) and distribution lists (EO and Full) and letterhead | Communications / IT
July 2 | x | Send attendee thank you email w/ evaluation link | Communications / IT
Week of July 13 | x | Send moderator and speaker thank you emails | Communications / IT
Week of July 13 | x | Send plenary speaker, sponsor, exhibitor, Mann thank you emails/letters | Stephanie / ED / Communications
Week of July 13 | x | Send reimbursement forms to sponsored travelers (reminder) | Program Staff / IT / Accounting / Mone'
Week of July 13 |  | Send EB date options for Fall Board Meeting | Stephanie / ED
Week of July 20 |  | Send EB conference call schedule | Stephanie / ED / Communications
Week of July 20 |  | All team post-cons reviewed with Beverly | Communications / Program / Accounting
DEADLINE – July 23 |  | Deadline for attendee evaluation submission | Evaluation / Communications
Week of August 3 | x | Post Presentations and announce prize & award winners | IT / Communications
Week of August 10 |  | Review evaluation results | Evaluation / Beverly
Week of August 24 | x | Post Position Statements Email to Memberships and Send Letters to Agencies | Meredith / Dhara / IT / Communications