| CSTE/CDC Advanced Management & Analysis of Influenza Surveillance Data Mentoring Program Work Plan |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Submission instructions: Country participants are to complete this document (in agreement with mentors) and submit the final version by Wednesday, May 9, 2018 to: - Monica Schroeder (CSTE): mschroeder@cste.org - Meg McCarron (CDC): dme8@cdc.gov - Kinda Zureick (CDC): kpf1@cdc.gov |  |  |  |  |  |  |  |  |
| Overview |  |  |  |  |  |  |  |  |
| Country Name: | GUAM |  | Date of submission |  |  |  | 5/8/2018 |  |
| Participant Name(s): | Alan Mallari, Anne Marie Santos |  |  |  |  |  |  |  |
| Mentor: | Karen Green Martin |  |  |  |  |  |  |  |
| Project Focus: | ILI/SARS cases screen and tested 2016-2017 |  |  |  |  |  |  |  |
| Contact Information |  |  |  |  |  |  |  |  |
|  | Name | Phone |  |  |  | Email |  |  |
| Participant(s) | Alan Mallari | 671-735-7140 |  |  |  | Alan.mallari@dphss.guam.gov |  |  |
|  | Anne Marie Santos | 671-735-7153 |  |  |  | Annemarie.santos@dphss.guam.gov |  |  |
| Mentor | Karen Martin | 651-201-5537 |  |  |  | Karen.martin@state.mn.us |  |  |
| Project Overview |  |  |  |  |  |  |  |  |
| Describe your proposed project(s): | - Laboratory data transmission to CDC FluView - Standard Operating Procedures (SOP) top include Epidemiology - Acquiring denominator data |  |  |  |  |  |  |  |
| Goal #1: Coordinate data transmission to CDC FluView | Estimated completion date: Click or tap to enter a date. |  |  |  |  |  |  |  |
|  | Action Items |  |  |  | Timeline |  |  |  |
|  | Check email correspondence (Desiree) |  |  |  | June 2018 |  |  |  |
|  | Submit data requested by CDC |  |  |  | July 2018 |  |  |  |
|  | Establish transfer of data |  |  |  | August 2018 |  |  |  |
| Goal #2: Standard Operating Procedures (SOP) to include Epidemiology | Estimated completion date: Click or tap to enter a date. |  |  |  |  |  |  |  |
|  | Action Items |  |  |  | Timeline |  |  |  |
|  | Collaborate with Epidemiologist and combine SOPs |  |  |  | August 2018 |  |  |  |
|  | Create documents and SOP drafts |  |  |  | September 2018 |  |  |  |
|  | Share drafts with Mentor Karen Martin |  |  |  | October 2018 |  |  |  |
| Goal #3: Acquiring denominator data | Estimated completion date: Click or tap to enter a date. |  |  |  |  |  |  |  |
|  | Action Items |  |  |  | Timeline |  |  |  |
|  | Explore meaningful use of NBS data |  |  |  | June 2018 |  |  |  |
|  | Capture robust information and cases from Hospitals |  |  |  | July 2018 |  |  |  |
|  | Calculate relative burden of diseases – positive percentage (%) |  |  |  | August 2018 |  |  |  |
| Describe any challenges you anticipate: | Locally, Guam Department of Public Health, not required to state “Village”. |  |  |  |  |  |  |  |
| Next Steps |  |  |  |  |  |  |  |  |
| List your next steps: | Action Item |  |  | Owner |  |  |  | Due date |
|  | Goals leading to refining laboratory data into graphical data |  |  | PH Lab Administrator Microbiologist |  |  |  | December 2018 |
|  | Descriptive Epidemiology |  |  | Epidemiologist |  |  |  | December 2018 |
|  | Accomplish goals with Quarterly Developments |  |  | PH Lab Administrator Microbiologist |  |  |  | April 2019 |
| What is your plan for follow-up? (e.g. phone call, email, etc.) | - Email (at least monthly) - Phone calls (as needed) - POC meetings as scheduled - Monthly Progress Report to CSTE via Karen - Informal schedule (casual FYI emails Cc Karen when emailing Desiree) |  |  |  |  |  |  |  |

| CSTE/CDC Advanced Management & Analysis of Influenza Surveillance Data Mentoring Program Update |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Submission instructions: - Country participants are to complete this document and submit via email to mentor - Mentors are to review the contents, add notes, and submit final version by the end of the month to: - Monica Schroeder (CSTE): mschroeder@cste.org - Meg McCarron (CDC): dme8@cdc.gov - Kinda Zureick (CDC): kpf1@cdc.gov |  |  |  |  |  |
| Overview |  |  |  |  |  |
| Country Name: | GUAM | Date of Update: |  | 5/8/2018 |  |
| Participant Name(s): | Alan Mallari, Anne Marie Santos |  |  |  |  |
| Mentor: | Karen Green Martin |  |  |  |  |
| Project Focus: | Explore meaningful use of NBS data |  |  |  |  |
| Overview of Work |  |  |  |  |  |
| Action items completed since last update: | Ongoing exploration of meaningful use of NBS data |  |  |  |  |
| Action items started since last update: | Start communication and exploration of the NBS – National Electronic Disease Surveillance System (NEDSS) Base System – under Guam Public Health Epidemiology and Laboratory Capacity (ELC) Program team and CDC NBS POCs. |  |  |  |  |
| Other progress made since last update: | Collaborate with Epidemiologist (part-time status) to combine SOPs. ELC Program supervisor and Guam Department of Public Health administration ongoing recruitment for full time Epidemiologist. |  |  |  |  |
| Challenges |  |  |  |  |  |
| Describe any challenges incurred since last update: | Epidemiologist is part-time and processing papers for retirement plans by September 2018. |  |  |  |  |
| Describe any challenges anticipated in near future: | Additional staff (bioinformatician) dedicated to creating and developing graphical data may be needed. |  |  |  |  |
| Next Steps |  |  |  |  |  |
| List your next steps: | Action Item |  | Owner |  | Due date |
|  | Capture data via NBS System |  | Microbiologist |  | June 2018 |
|  | Capture robust information and cases from Hospitals |  | Microbiologist Epidemiologist |  | July 2018 |
|  | Calculate relative burden of diseases – positive percentage (%) |  | PH Lab Administrator Epidemioligst |  | August 2018 |
| Do you have a scheduled follow-up? When? How? (e.g. phone call, email, etc.) | Yes, by the week of June 18, 2018 via email. |  |  |  |  |
| For Mentor Use Only |  |  |  |  |  |
| Please insert your notes here. Include progress made, challenges you face, and any other relevant updates for CDC/CSTE. |  |  |  |  |  |