| CSTE/CDC Advanced Management & Analysis of Influenza Surveillance Data Mentoring Program Work Plan |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Submission instructions: Country participants are to complete this document (in agreement with mentors) and submit the final version by Wednesday, May 9, 2018 to: - Monica Schroeder (CSTE): mschroeder@cste.org - Meg McCarron (CDC): dme8@cdc.gov - Kinda Zureick (CDC): kpf1@cdc.gov |  |  |  |  |  |  |  |  |
| Overview |  |  |  |  |  |  |  |  |
| Country Name: | PARAGUAY |  | Date of submission |  |  |  | 5/2/2018 |  |
| Participant Name(s): | Marta von Horoch |  |  |  |  |  |  |  |
| Mentor: | Karen Martin |  |  |  |  |  |  |  |
| Project Focus: | Risk factors calculation |  |  |  |  |  |  |  |
| Contact Information |  |  |  |  |  |  |  |  |
|  | Name | Phone |  |  |  | Email |  |  |
| Participant(s) | Marta von Horoch | +595981500276 |  |  |  | martavhv@gmail.com |  |  |
|  | Agueda Cabello | +59521204743 |  |  |  | aguedacabello@yahoo.com |  |  |
| Mentor | Karen Martin | (651)201-5537 |  |  |  | Karen.martin@health.state.mn.us |  |  |
| Project Overview |  |  |  |  |  |  |  |  |
| Describe your proposed project(s): | Calculate risk factors by comparing influenza seasons with predominance of H1 vs H3. |  |  |  |  |  |  |  |
| Goal #1: Define the years of predominance of each subtype and prepare the database | Estimated completion date: 8/31/2018 |  |  |  |  |  |  |  |
|  | Action Items |  |  |  | Timeline |  |  |  |
|  | Define the variables for the analysis. |  |  |  | 6/15/2018 |  |  |  |
|  | Perform data quality assurance/ quality control. |  |  |  | 7/15/2018 |  |  |  |
|  | Perform the descriptive, frequency analysis. |  |  |  | 8/31/2018 |  |  |  |
|  | Identify the risk factors to analyze. |  |  |  | 8/31/2018 |  |  |  |
| Goal #2: Analysis of risk factors | Estimated completion date: 11/30/2018 |  |  |  |  |  |  |  |
|  | Action Items |  |  |  | Timeline |  |  |  |
|  | Calculation of risk factors measure of association. |  |  |  | 9/30/2018 |  |  |  |
|  | Statistical Testing of Risk Factor Measures of Association |  |  |  | 10/30/2018 |  |  |  |
|  | Analyze Multiple Possible Risk Factors: Stratified Analysis, Multivariable regression models |  |  |  | 11/30/2018 |  |  |  |
| Goal #3: Interpret and Make a manuscript with the results | Estimated completion date: 3/31/2019 |  |  |  |  |  |  |  |
|  | Action Items |  |  |  | Timeline |  |  |  |
|  | Discussion of the findings |  |  |  | 01/31/2019 |  |  |  |
|  | Interpret the results |  |  |  | 02/28/2019 |  |  |  |
|  | Write the manuscript /Improve the annual report |  |  |  | 03/31/2019 |  |  |  |
| Describe any challenges you anticipate: | The routine of daily work Seasonal epidemics that my country faces Limited use of analysis tools Responsible for the surveillance of several events in my country |  |  |  |  |  |  |  |
| Next Steps |  |  |  |  |  |  |  |  |
| List your next steps: | Action Item |  |  | Owner |  |  |  | Due date |
|  | Meet with team to define appropriate variables |  |  |  |  |  |  |  |
|  | Establish tasks within the team. |  |  |  |  |  |  |  |
|  | Set up timeline for email communication |  |  |  |  |  |  |  |
| What is your plan for follow-up? (e.g. phone call, email, etc.) | E-mail, eventually phone call. |  |  |  |  |  |  |  |

| CSTE/CDC Advanced Management & Analysis of Influenza Surveillance Data Mentoring Program Update |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Submission instructions: - Country participants are to complete this document and submit via email to mentor - Mentors are to review the contents, add notes, and submit final version by the end of the month to: - Monica Schroeder (CSTE): mschroeder@cste.org - Meg McCarron (CDC): dme8@cdc.gov - Kinda Zureick (CDC): kpf1@cdc.gov |  |  |  |  |  |
| Overview |  |  |  |  |  |
| Country Name: |  | Date of Update: |  | Click or tap to enter a date. |  |
| Participant Name(s): |  |  |  |  |  |
| Mentor: |  |  |  |  |  |
| Project Focus: |  |  |  |  |  |
| Overview of Work |  |  |  |  |  |
| Action items completed since last update: |  |  |  |  |  |
| Action items started since last update: |  |  |  |  |  |
| Other progress made since last update: |  |  |  |  |  |
| Challenges |  |  |  |  |  |
| Describe any challenges incurred since last update: |  |  |  |  |  |
| Describe any challenges anticipated in near future: |  |  |  |  |  |
| Next Steps |  |  |  |  |  |
| List your next steps: | Action Item |  | Owner |  | Due date |
| Do you have a scheduled follow-up? When? How? (e.g. phone call, email, etc.) |  |  |  |  |  |
| For Mentor Use Only |  |  |  |  |  |
| Please insert your notes here. Include progress made, challenges you face, and any other relevant updates for CDC/CSTE. |  |  |  |  |  |