| CSTE/CDC Advanced Management & Analysis of Influenza Surveillance Data Mentoring Program Update |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Submission instructions: - Country participants are to complete this document and submit via email to mentor - Mentors are to review the contents, add notes, and submit final version by the end of the month to: - Monica Schroeder (CSTE): mschroeder@cste.org - Meg McCarron (CDC): dme8@cdc.gov - Kinda Zureick (CDC): kpf1@cdc.gov |  |  |  |  |  |
| Overview |  |  |  |  |  |
| Country Name: | Tunisia | Date of Update: |  | 6/29/2018 |  |
| Participant Name(s): | Cherif Amal / Bouabid Leila |  |  |  |  |
| Mentor: | Kinda Zureick/ Meg McCarron |  |  |  |  |
| Project Focus: | Improvement of the quality of our influenza surveillance data |  |  |  |  |
| Overview of Work |  |  |  |  |  |
| Action items completed since last update: | We have completed our first draft of the ILI data using the aggregate weekly reporting sheet. We have added the variables missing in our first draft comparing to the aggregate form . |  |  |  |  |
| Action items started since last update: | We are discussing with our supervisors the interest of including or not some variables existing in the aggregate weekly reporting sheet such as the number of ILI cases tested by sex on each age group |  |  |  |  |
| Other progress made since last update: |  |  |  |  |  |
| Challenges |  |  |  |  |  |
| Describe any challenges incurred since last update: | To reformate our weekly lab database and to standardize some variable as well as for the ILI Database ( until now for the variable: ILI center, we are using the governorate name instead of the name of the ILI sites ). |  |  |  |  |
| Describe any challenges anticipated in near future: | ILI DATABASE : the variable week of the declaration should be expressed not the way on the aggregated forms (from the date.... to the date... ) but in ISO week number. |  |  |  |  |
| Next Steps |  |  |  |  |  |
| List your next steps: | Action Item |  | Owner |  | Due date |
|  | Obtaining the complete lab database |  |  |  |  |
|  | Removing our ILI data to the new ILI input mask after validation |  |  |  |  |
|  | Reformate the weekly lab database |  |  |  |  |
| Do you have a scheduled follow-up? When? How? (e.g. phone call, email, etc.) |  |  |  |  |  |
| For Mentor Use Only |  |  |  |  |  |
| Please insert your notes here. Include progress made, challenges you face, and any other relevant updates for CDC/CSTE. | Project is progressing- held 2 calls and have communicated back and forth via email. Afif, Amal, and Leila have received buy in from the Steering Committee for this project and we expect more progress to be made in the coming months. Meg & Kinda to do a site visit to Tunisia in August, which may allow for some hands-on time for this project. |  |  |  |  |