| CSTE/CDC Advanced Management & Analysis of Influenza Surveillance Data Mentoring Program Update |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Submission instructions: - Country participants are to complete this document and submit via email to mentor - Mentors are to review the contents, add notes, and submit final version by the end of the month to: - Monica Schroeder (CSTE): mschroeder@cste.org - Meg McCarron (CDC): dme8@cdc.gov - Kinda Zureick (CDC): kpf1@cdc.gov |  |  |  |  |  |
| Overview |  |  |  |  |  |
| Country Name: | Bhutan | Date of Update: |  | 7/25/2018 |  |
| Participant Name(s): | Sangay Zangmo |  |  |  |  |
| Mentor: | Katherine Roguski |  |  |  |  |
| Project Focus: | - Estimation of baseline and alert threshold for influenza activity in Bhutan |  |  |  |  |
| Overview of Work |  |  |  |  |  |
| Action items completed since last update: | - Created charts for baseline determination following WHO method, using the following data: - Percentage positive of ILI samples - Weekly ILI proportions - Weekly SARI proportions - Determined periods for individual years where the data was above seasonal threshold for each year |  |  |  |  |
| Action items started since last update: | - Baseline charts following WHO method, using data from laboratory positive ILI samples, weekly ILI and SARI proportions |  |  |  |  |
| Other progress made since last update: |  |  |  |  |  |
| Challenges |  |  |  |  |  |
| Describe any challenges incurred since last update: |  |  |  |  |  |
| Describe any challenges anticipated in near future: | Competing work priorities |  |  |  |  |
| Next Steps |  |  |  |  |  |
| List your next steps: | Action Item |  | Owner |  | Due date |
|  | - Finalize and submit 1st project |  | Sangay Zangmo |  | Aug 3, 2018 |
|  | - Incorporation of the results into regular reporting system |  | Sangay Zangmo |  | Aug 10, 2018 |
|  | - Data cleaning for 2nd project |  | Sangay Zangmo |  | Aug 17, 2018 |
|  | - Plot weekly retrospective data by regions |  | Sangay Zangmo |  | Aug 24, 2018 |
|  | - Review by mentor |  | Katherine Roguski |  | Aug 27, 2018 |
| Do you have a scheduled follow-up? When? How? (e.g. phone call, email, etc.) | Phone call with mentor: Fourth week of August |  |  |  |  |
| For Mentor Use Only |  |  |  |  |  |
| Please insert your notes here. Include progress made, challenges you face, and any other relevant updates for CDC/CSTE. | Sangay is on target with her mentorship goals. The tasks she is undertaking for project one (seasonal baseline) have already been applicable to the work of her larger group, as they try to determine the best time for influenza vaccination timing. She should be able to present the results of project one to her group within the next two weeks. |  |  |  |  |