| CSTE/CDC Advanced Management & Analysis of Influenza Surveillance Data Mentoring Program Update |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Submission instructions: - Country participants are to complete this document and submit via email to mentor - Mentors are to review the contents, add notes, and submit final version by the end of the month to: - Monica Schroeder (CSTE): mschroeder@cste.org - Meg McCarron (CDC): dme8@cdc.gov - Kinda Zureick (CDC): kpf1@cdc.gov |  |  |  |  |  |
| Overview |  |  |  |  |  |
| Country Name: | JAMAICA | Date of Update: |  | 6/30/2018 |  |
| Participant Name(s): | KELLY-ANN GORDON-JOHNSON |  |  |  |  |
| Mentor: | KRISTA KNISS |  |  |  |  |
| Project Focus: | DATA QUALITY IMPROVEMENT & ADVANCED DATA ANALYSIS |  |  |  |  |
| Overview of Work |  |  |  |  |  |
| Action items completed since last update: | DEVELOP PROCESS FLOW MAP |  |  |  |  |
| Action items started since last update: | REVIEW COMPLETENESS OF RISK FACTOR DATA |  |  |  |  |
| Other progress made since last update: |  |  |  |  |  |
| Challenges |  |  |  |  |  |
| Describe any challenges incurred since last update: | CHALLENGES PRIMARILY RELATED TO COMPLETING STATED ACTION ITEMS IN THE STIPULATED TIMEFRAME DUE TO COMPETING PRIORITIES |  |  |  |  |
| Describe any challenges anticipated in near future: | NO ANTICIPATED CHALLENGES AT THIS TIME |  |  |  |  |
| Next Steps |  |  |  |  |  |
| List your next steps: | Action Item |  | Owner |  | Due date |
|  | REVIEW COMPLETENESS OF RISK FACTOR DATA |  | K. GORDON-JOHNSON |  | 6/30/2018 |
|  | REVIEW VARIATIONS IN PEAKS OVER A TEN YEAR |  | K. GORDON-JOHNSON |  | 7/31/2018 |
|  | DEVELOP QUALITY CONTROL/QUALITY ASSURANCE PLAN |  | K. GORDON-JOHNSON |  | 7/31/2018 |
| Do you have a scheduled follow-up? When? How? (e.g. phone call, email, etc.) | THE PARTICIPANTS & MENTOR WILL HAVE FOLLOW-UP DISCUSSIONS REGARDING ACTION BY EMAIL. |  |  |  |  |
| For Mentor Use Only |  |  |  |  |  |
| Please insert your notes here. Include progress made, challenges you face, and any other relevant updates for CDC/CSTE. | Kelly-Ann provided me with a copy of the process map that she developed, but I think she could make a few things a bit more clear. I have provided her some feedback on this. We have not done any data work yet as she has been too busy with competing priorities. I have asked her to share some data with me, but she has not done so yet. She plans to next review the completeness of her risk factor data to determine whether she can do some risk factor analyses. I think the biggest challenge is that she has too ambitious of a plan with both of us having competing priorities. We will do our best to move forward with the planned activities. |  |  |  |  |