ARSTF Core Group Call
Wednesday, January 24, 2018

Attendees: Rich, Zints, Wes, Pete, Brooke, Marion, Dan, Dawn, Lesliann 

Minutes:

1. Roll
2. Minutes from last week's meeting
a. To Do: Send Meredith and Rich any questions or concerns on minutes from last week
3. Finalizing the Proceedings
a. Anything else needed to finalize? 
b. Dawn sent along revisions to Rich today (1/24)
c. Rich will finalize after conferring with Informatics workgroup on 2/2 call.
4. Status of the Assessment Plan workbook
a. Dawn’s edits to the Proceedings will help populate some of the Informatics portions in the spreadsheet
b. Rich will look into additional resources to put into the assessment plan, including resources in the Informatics workgroup Basecamp
5. The Assessment Plan proper
a. Rich will send out a more fleshed out version of the Assessment plan for review early next week.
6. Status of scheduling the Plenary Task Force call
a. To Do: Meredith to send out poll soon, want to ensure folks don’t confuse the two doodle polls (one for plenary call, one for in-person meeting)
7. Status of scheduling the in-person meeting
a. Meredith sent out scheduling poll today, closing January 26th. CSTE staff will narrow down dates and relay them on next week’s core group call
8. Data Flow Diagram status
a. Wes sent out PowerPoint with updated data flow diagrams, incorporating input for more delineation between current pathways and potential future pathways
b. Updated integrated flow diagram, beginning to add in layered diagrams
c. Wes is also in the process of drafting additional, more detailed flow diagrams, and will send those out in the next couple of weeks 
d. Also working on moving these to a web-based platform so that people will be able to access/review more easily
e. To Do: provide comments on work so far to Wes by next core group call
9. FDA SHIELD Meeting
a. Two-day meeting with large informatics focus. Originally scheduled for earlier this week, but government shutdown prompted a reschedule. 
b. Scott Troppy to most likely attend the rescheduled meeting on ARSTF’s behalf
10. CP-CRE MMG template being submitted
a. Template completed, lingering questions resolved (e.g., valid values for clinical sites)
b. Meredith submitting this week
c. Noted challenge: Delayed OMB approval for receiving certain data for this condition
d. Full launch for MMG will be 2019, with piloting beforehand
· Currently using gen V2 to collect this info for 2018
· Question: Will CDC be able to accept susceptibly data? Answer: No, will have to wait until 2019 to receive these data. However, states may have the option to send 2018’s data once MMG is fully launched in 2019
· Condition/event codes are ready (in introductory tab)
e. Should we share copies of the MMG template with this workgroup? How widely (or not) should this be distributed?
· Since this is preliminary, would not want programs to be building off this. Might be better to hold off sharing widely
· Can however share with core group members. To Do: Meredith to send submitted template to core group for reference, clearly marked “draft”
11. Work Group meetings, a combined meeting?
a. CSTE staff and workgroup leads will talk this Friday (1/26)
b. Work towards a combined call in late February
12. Other
13. Adjourn
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