ARSTF Core Group Call

Wednesday, January 24, 2018

Attendees: Rich, Zints, Wes, Pete, Brooke, Marion, Dan, Dawn, Lesliann

Minutes:

- Roll

- Minutes from last week's meeting

  - To Do: Send Meredith and Rich any questions or concerns on minutes from last week

- Finalizing the Proceedings

  - Anything else needed to finalize?

  - Dawn sent along revisions to Rich today (1/24)

  - Rich will finalize after conferring with Informatics workgroup on 2/2 call.

- Status of the Assessment Plan workbook

  - Dawn’s edits to the Proceedings will help populate some of the Informatics portions in the spreadsheet

  - Rich will look into additional resources to put into the assessment plan, including resources in the Informatics workgroup Basecamp

- The Assessment Plan proper

  - Rich will send out a more fleshed out version of the Assessment plan for review early next week.

- Status of scheduling the Plenary Task Force call

  - To Do: Meredith to send out poll soon, want to ensure folks don’t confuse the two doodle polls (one for plenary call, one for in-person meeting)

- Status of scheduling the in-person meeting

  - Meredith sent out scheduling poll today, closing January 26th. CSTE staff will narrow down dates and relay them on next week’s core group call

- Data Flow Diagram status

  - Wes sent out PowerPoint with updated data flow diagrams, incorporating input for more delineation between current pathways and potential future pathways

  - Updated integrated flow diagram, beginning to add in layered diagrams

  - Wes is also in the process of drafting additional, more detailed flow diagrams, and will send those out in the next couple of weeks

  - Also working on moving these to a web-based platform so that people will be able to access/review more easily

  - To Do: provide comments on work so far to Wes by next core group call

- FDA SHIELD Meeting

  - Two-day meeting with large informatics focus. Originally scheduled for earlier this week, but government shutdown prompted a reschedule.

  - Scott Troppy to most likely attend the rescheduled meeting on ARSTF’s behalf

- CP-CRE MMG template being submitted

  - Template completed, lingering questions resolved (e.g., valid values for clinical sites)

  - Meredith submitting this week

  - Noted challenge: Delayed OMB approval for receiving certain data for this condition

  - Full launch for MMG will be 2019, with piloting beforehand

    - Currently using gen V2 to collect this info for 2018

    - Question: Will CDC be able to accept susceptibly data? Answer: No, will have to wait until 2019 to receive these data. However, states may have the option to send 2018’s data once MMG is fully launched in 2019

    - Condition/event codes are ready (in introductory tab)

  - Should we share copies of the MMG template with this workgroup? How widely (or not) should this be distributed?

    - Since this is preliminary, would not want programs to be building off this. Might be better to hold off sharing widely

    - Can however share with core group members. To Do: Meredith to send submitted template to core group for reference, clearly marked “draft”

- Work Group meetings, a combined meeting?

  - CSTE staff and workgroup leads will talk this Friday (1/26)

  - Work towards a combined call in late February

- Other

- Adjourn