Notes from February 20, 2019 ARSTF core group call, 4:00 – 5:00 pm

On the call:   Dan Pollack, Pete Shult, Jeff Engel, Wes Kennemore, Lesliann Helmus, Marion Kainer-tanned and rested, Dawn Sievert, Kelly Wroblewski, Brooke Beaulieu, Rich Melchreit

- Minutes from February 6th were reviewed and accepted with a typo correction.

- Current status of the Work Groups:

  - In general – all began calls last week, enrollment numbers 14-26 per WG, developing tactical “to do” list plans, arranging for briefings by SMEs, are aware their focus should be to accomplish what they can by end of June, and we will report in the Year 3 final report on their advice for next steps beyond that point.

  - Work group 1: Standardization, ELR, accession numbers – Scott Troppy is lead, group is working on assigning different tasks related to recommendation implementation to different WG members.

  - Work Group 2: Suppression, breakpoints – Megin Nichols is lead, made some headway on identifying vendor and manufacturer groups to approach for collaboration, need access to CLSI M100 (which is free online).

  - Work Group 3: MMG - finished.

  - Work Group 4: NHSN, tracking registries – DJ Shannon is lead, Amy Webb from NHSN will give background information on AUR uptake issues.  The Group will get briefings from XDRO registry (Erica Runningdeer), MAVEN (Scott Troppy, MA), and NBS-REDCap Marion Kainer will be invited.  DPQP is having discussions on this issue, Dan Pollack said that he, Wes Kennemore, and Sheri Tejeda, would be happy to present to the group on behalf of DHQP.

  - Work Group 5: Colonization, jurisdictional cumulative antibiograms – Brooke and Rich M had a call with Rich Danila to set up a telephonic “focus group” of State Epis both in favor and against colonization being included in CSTE surveillance standards to dialog and explore the issue.  This call will be held in the next two weeks, and perhaps followed by nationwide survey of State Epidemiologists (Rich M has drafted a qualitative survey). Eventually it may lead to a Policy Brief or Statement on this issue. Marion Kainer and Al DeMaria and perhaps Don Weiss (if he would like to be on the call, he is the Lead member of the WG 5), along with selected state Epidemiologists identified by Rich Danila.   Statewide antibiograms – the group is collecting background information and looking to get access to the CSLI M39 the guidance on antibiograms.  They are considering a nationwide survey of HAI/AR Coordinators and possible guidance to develop a toolkit.

- The JPHIT white paper on how to promote increased use of the NHSN AR module has been approved for placement on the ARSTF website.  Staff are considering what to add to the ARSTF website to update it to reflect Year 3 activities.  Core WG members are encouraged to email suggestions to Kelly, Brooke, or Rich.

- The Core WG agree it is time to hold a Plenary call to update all TF members and encourage any who would like to get involved o a Work Group, but haven’t yet, to sign up.  The call will be held mid or late-March.

- Sustainability – CDC DHQP met with CSTE leadership and DHQP expressed interest in keeping CORHA and the ARSTF separate, and to likely continue it in the future (after July 31).  CSTE will see how that might be supported when the CDC’s Cooperative Agreement Funding Opportunity Announcement comes out in March.

- The AMR Challenge memo review is pending coordination with the other memo going out, the latter to Deputy SHOs.

- The LA County abstract for the antibiogram roundtable was accepted for review.  Now it is in the review process.  Of course, there are no guarantees on an outcome of the review, but it is encouraging it will at least get a chance to compete for selection.

- Anticipated Core WG absences:

  - Jeff – away first half of April

  - Wes - first week of May and Memorial Day week

  - Pete week of March 17th, on vacation, but still on the ball (but not snow)

  - Marion, SHEA April 24-26

  - Rich  - May 8-15

- Next Co-chair and staff call will be next Wednesday, February, 27  at 4-5 pm.

- Next Core WG call will be Wednesday, 3/6/19 at 4-5 pm.