Outline for an Annual Plan (6/28/17)

July 1, 2017 – June 30, 2018

Strategic Objectives for the 12-month period (from the Strategic Profile)

## Governance Structure

Strategic Objective E-1:  Establish and implement a governance structure.

Strategic Objective A-6:  Establish roles, responsibilities and priorities of public health and the clinical sector.

## Lab Data to Public Health

Strategic Objective B-4:  Enable capture of data using standardized vocabulary codes for new tests and other antimicrobial resistance data.

Strategic Objective B-5:  Implement a strategy to extract suppressed antimicrobial susceptibility test results.

Strategic Objective C-4:  Establish and align standards for data collection, transmission and provisioning.

Strategic Objective A-5:  Increase public health, lab and clinical informatics and bioinformatics capacity.

## Public Health Informatics Tools

Strategic Objective A-5:  Increase public health, lab and clinical informatics and bioinformatics capacity.

Strategic Objective C-1:  Evaluate, enhance and promote existing systems, processes and tools.

Strategic Objective D-2:  Integrate epi, lab and clinical data.

Strategic Objective C-2:  Leverage shared technical infrastructure and services.

PART 1: LOGISTICS

Governance Structure

- Procedure and process document for the ARSTF – Version 1.0 completed 6/21/17

- Identification of Co-chairs for ARSTF – done 5/31/17

- Recruit Task Force membership – done 5/31/17

- Form workgroups, choose leader and deputy leaders

  - Core Work Group – done

  - Lab Data to PH WG

    - Consists of ARLN committee

    - Leader already identified

    - Co-chairs call with ALRN group in June

    - Register members of work group and intro call in July

  - Informatics WG

    - Approach SI Committees of CSTE/APHL for names

    - Ensure ELR, EHR vendors included

    - Register members of work group and intro call in July

- Onboard new members - ongoing

Meeting Schedule

- Core Work Group - weekly calls

- Full TF quarterly (calls, perhaps in person)

  - We have 25 slots two meetings (fall and spring) in Atlanta

- Workgroups

  - Bi-weekly calls

- Staffing of WG meetings:

  - Monica and/or Rich attend Informatics’ WG calls

  - Pete Shult and Kelly Wroblewski attend Lab calls

  - All will participate in Core WG

PART 2: WORK GROUP ACTIVITIES

Core Work Group

- Review progress of workgroups – major standing agenda items

Strategic Objective A-6:  Establish roles, responsibilities and priorities of public health and the clinical sector.

  - Will need input from the other two work groups on details for this objective’s assessment and recommendations

  - Core WG will oversee “Initiate actions”

Lab Data to Public Health Work Group

Objectives:

  - Strategic Objective B-4:  Enable capture of data using standardized vocabulary codes for new tests and other antimicrobial resistance data.

  - Strategic Objective B-5:  Implement a strategy to extract suppressed antimicrobial susceptibility test results.

  - Strategic Objective C-4:  Establish and align standards for data collection, transmission and provisioning.

  - Strategic Objective A-5:  Increase public health, lab and clinical informatics and bioinformatics capacity.

Process:

  - Workgroup workplan – prepare in July and then present to Lead and Deputy lead for discussion and editing

    - Strategic objectives

    - Expected outcomes and process deliverables

    - Timeline

Assessment:

    - Assessment of initial status related to objective (WG members, surveys, focus groups, key informants)

    - Report on assessment to CWG/TF

Recommendations

  - Content of recommendations

    - How to address barriers

    - How to exploit/expand facilitating factors

  - Actions/responsible sectors and organizations with timeline for action

  - Report on recommendations to Core WG/TF

Initiate actions

  - Report on actions completed by 6/30/18 to CWG/TF

Public Health Information Tools Work Group

Strategic Objective A-5:  Increase public health, lab and clinical informatics and bioinformatics capacity.

Strategic Objective C-1:  Evaluate, enhance and promote existing systems, processes and tools.

Strategic Objective D-2:  Integrate epi, lab and clinical data.

Strategic Objective C-2:  Leverage shared technical infrastructure and services.

Process:

  - Workgroup workplan – prepare in July and then present to Lead and Deputy lead for discussion and editing

    - Strategic objectives

    - Expected outcomes and process deliverables

    - Timeline

Assessment:

    - Assessment of initial status related to objective (WG members, surveys, focus groups, key informants)

    - Report on assessment to CWG/TF

Recommendations

  - Content of recommendations

    - How to address barriers

    - How to exploit/expand facilitating factors

  - Actions/responsible sectors and organizations with timeline for action

  - Report on recommendations to Core WG/TF

Initiate actions

  - Report on actions completed by 6/30/18 to CWG/TF

- GANTT Chart: pending