Summary of In-person Meeting Proceedings

Informatics call 1/5/18

- Proceedings will be written, discussion will lead to an Assessment Plan

- Timeline

  - Proceedings and assessment plan early January

  - Assessment by mid-April

  - Another in person meeting in late April or mid-May

  - Recommendations drafted at second In-person meeting

  - Recommendations edited after feedback by early June and posted

  - Assessment and recommendations discussed at CSTE Annual Conference mid-June

  - Assessment and recommendations finalized June 30

- CP-CRE

  - The Message Mapping Guide is nearly complete, reviewed and discussed

  - Some of the specimen sources are overlapping, feedback noted, will be discussed and finalized by the Workgroup after this In-person meeting

  - Will be ready to send to CDC January 1 or shortly thereafter

- Strategic objectives:

  - See revision document

  - Not clear on what additional text needs to be added to “One Health” and “vendors”

- Data Flow Diagram

- Breakouts

  - Each objective discussed

    - Stakeholders

    - Questions

    - Methods

    - Timeline

    - Instructions, documents to procure

  - A lot of possible existing documents to procure

  - Good list of stakeholders to involve, need more Vendor participation, piggyback on their meetings?

  - Initiative in development need to be better understood and incorporated (ex. eTOR)

  - Discussion on whether to table bioinformatics for now and just focus on informatics

- Parking lot/other

  - Benefit from continued cross-work group discussion (share expertise)

1/4/18 ver 2