## Sheet1
Example of Assessment Plan Brainstorming Output
Lab Work Group
Objective | What do you want to know - Questions | Who do you want to ask - Stakeholder class | Who do you want to ask - Stakeholder individuals | Methods | Who can help - Task Force and beyond | Timeline |  | Additional instructions for staff
B-4 Enable capture of data using standardized vocabulary codes for new tests and ot+A5:B11her antimicrobial resistance data. | F0r which of the following* data elements do you currently utilize standard codes (e.g. LOINC)? | clinical laboratories; public health laboratories; commercial laboratories/ all laboratories should be partnered with IT staff in completing survey/ initial engagement should come from someone the labs know | Subset of PHLs and Clinical laboratories; 4 major commercial laboratories (ARUP, Lab Corp, Mayo, Quest) | Survey |  |  |  | *Workgroup to develop list of values that require standardized codes
Sub objective list | Do these codes existing intrinsically within your LIS or do you map to them within the EMR? | see above | see above | see above |  | Collect documents | mid Jan
| When new tests are implemented who in your laboratory makes the decision on which codes to implement (local codes versus standard codes)? Responses could be Micro Director/ supervisor/ IT specialist/ follow vendor recommendation. | see above | see above | see above |  | Draft survey of stakeholders | early Feb
| When new tests are implemented how do you make the decision on which codes to implement (local codes versus standard codes)? Responses could include: follow vendor recommendations… | see above | see above | see above |  | Complete survey | mid March
| How long does new code implementation take? | see above | see above | see above |  | First draft assessment | late March
[6 empty] | Final draft accepted | early April
C-4 Establish and align standards for data collection, transmission and provisioning | No assessment questions for lab community | N/A
Sub objective list | What is the ideal ELR look like? | CSTE/ Informatics WG | Informatics WG | Joint teleconference? | Maine CSTE HAI Fellow on Task Force, wants to make this a Fellowship project | etc. | etc. | etc.
| What information is NOT included in a traditional ELR that PH would like to receive | CSTE/ Informatics WG | Informatics WG | Joint teleconference? | Informatics WG can give input on our informatics questions
B-5 Implement a strategy to extract suppressed antimicrobial susceptibility test results? | What AST Data are stored in the instrument? (MICs, interpretation, more?) | See B-4 use same group of labs | see B-4 | Survey
Sub objective list | What AST data are stored in the LIS? (MICs, interpretation, more?)
What AST data are stored in EMR? (MICs, interpretation, more?)
Where are breakpoints applied? (instrument versus LIS)
Where are MICs stored? (instrument versus LIS versus more(?))
Question on antibiograms/ which data suppressed ???
A-5 Increase public health, lab and clinical informatics and bioinformatics capacity? | What LIS are you currently using? | See B-4 use same group clinical and commercial labs; pull from existing PHL data | See B-4 use same group clinical and commercial labs; pull from existing PHL data | Survey
Sub objective list | What are your current staff resources to build ELR? (ask in regards to FTE?) |  |  | APHL NGS and LIMS data
Do you have funding dedicated to implementing ELR? (ask about amount?)
Do you currently perform Next Generation Sequencing in your micro or molecular biology section? For detection or monitoring of antimicrobial resistance?
If yes, what pipelines or software are you using for data analysis? And what approach are you using for storing NGS data?
| How are reports from commercial laboratories stored in LIMS? How are they made available in result report to physicians, EMR and/or ELR? | for clinical and PHLs only.
Not necessarily associated with question | Who is responsible for reporting AR?