## Slide 1: ARSTF Work Group 1
Work Group Kickoff Call
February 14, 2019

## Slide 2: Introductions
Work Group lead:
  Scott Troppy, MA
Work Group Staff
  Kelly Wroblewski, APHL
  Rich Melchreit, CSTE
Members (around the “room”)

## Slide 3: Status of the Task Force’s work
Year 2 recommendations made and publicized
  See CSTE website Task Force page: https://cdn.ymaws.com/www.cste.org/resource/resmgr/arstf/ARSTF_Year_2_Report_and_Reco.pdf
  6 topic areas
  18 recommendations
Other relevant documents – available on CSTE website
  Public health agency roles and responsibilities tables
  JPHIT whitepaper
  CP-CRE position statement, surveillance best practices 2017, operational guidance
Recommendations format (to support implementation)
  Lead organization
  Stakeholders
  Objectives/tasks for year 3 work
Year 3 through June-July 2019

## Slide 4: Work Groups
Five workgroups
  each take on 1-3 topics from Year 2 Report and Recommendations
  1-several recommendations per topic
Key tasks:
  Engage lead organization and stakeholders
  Engage and get commitment from stakeholders
  Get the recommendations(s) onto the stakeholder's workplan
See the “charge document” handout, ready reference, summary

## Slide 5: List of Work Groups
WG 1 – Standards, ELR, linking/accession #s – Scott Troppy
WG2 – Data “suppression”, breakpoints – Megin Nicols
WG3 – CP-CRE MMG (nearly finished) – Scott Troppy, DJ Shannon
WG4 – NHSN/tracking registries - DJ Shannon
WG5 - Surveillance scope (“colonization,” antibiograms) – Don Weiss
Core WG - sustainability

## Slide 6: Work Group members
A lead person (from the TF)
Up to 14 others, don’t have to be TF member (WG 5 has 24)
Types of individuals
  ARS stakeholders – clinical, public health epidemiology, laboratory, informatics
  Relationships with stakeholder organizations will be helpful, not required
Time commitment for Work Group member – couple of hours per week, usually biweekly calls once up and running anticipated, sometimes weekly at crunch time
Activities – Work Group workplan, review of documents, act as ambassadors with stakeholders (meetings, calls, present), lead WG member attend some conference calls with ARTSF Core WG
Staffing – CSTE, APHL

## Slide 7: Work Group Leads
Responsibilities:
  Approve agendas
  Control the floor during calls, manage time
  Point of contact for staff and members between calls
  Sign off on documents prepared by the WG (plan, progress reports, slide sets)
  Give progress updates/discussions with Core WG – approximately once every 4-6 weeks
Time commitment – on average, 2 hours per week in addition to group call time
Staffing:
One lead staff (Brooke, Kelly)
  Rich assists, backup
  Logistics
    Email and document preparation and distribution
    Scheduling of conference calls of group, calls with stakeholders, etc.
Governance
  Co-chairs (CSTE, CDC, APHL)
  Core Work Group

## Slide 8: Benchmarks 2019
  Form Work Groups – by February 8
  Start Work Group calls – by February 22
  Status reports to Core WG – starting March 1
  Items for inclusion in CSTE Annual Conference Roundtable (if accepted) – by May 29
  CSTE Annual Conference Roundtable – by June 6
  Year 3 Report draft – by June 30
  Year 3 Report final – by July 31

## Slide 9: Work group 1’s scope, activities (1)
Terminology/Data Standards, Use of Standardized Codes |  |  | 
# | Recommendation | Lead | Stakeholders
1 | Identify/create LOINC codes for all relevant tests and SNOMED codes for pathogens and corresponding test results for all AR pathogens and AST, and a process for timely establishment of these codes. | APHL | HL7, Regenstrief Institute (LOINC), National Library of Medicine (SNOMED), APHL, JPHIT, LIMS vendors, state lab and clinical lab directors
1A | Develop processes for ensuring that LOINC/SNOMED codes are available for non-proprietary tests. | APHL | HL7, Regenstrief Institute (LOINC), National Library of Medicine (SNOMED), APHL, JPHIT, LIMS vendors, state lab and clinical lab directors
1B | Encourage CLSI or FDA to require manufacturers to recommend a standard three-letter antibiotic code when submitting new compounds for review. CLSI or FDA should also submit a letter antibiotic code when submitting new compounds for review. CLSI or FDA should also submit a request to the Regenstrief Institute for the creation of relevant LOINC codes for new compounds under review. | FDA and CLSI | FDA, CLSI, HL7, Regenstrief Institute, National Library of Medicine, APHL, JPHIT, pharmaceutical companies, diagnostics manufacturers
1C | Develop a standardized approach for submitting for LOINC codes for new/emergent pathogens. | Regenstrief Institute | Regenstrief Institute, APHL, CDC, Lab instrument manufacturers, LIMS vendors, state lab and clinical lab directors, state AR programs, WHONET
1D | Support efforts to routinely include standard codes in package inserts for proprietary tests (e.g. SHIELD) | FDA | 
1E | Routinely include LOINC/SNOMED code recommendations in laboratory guidance documents (e.g. CLSI) | CLSI | CLSI, CDC, HL7, Regenstrief (LOINC), National Library of Medicine, APHL, JPHIT, LIMS vendors, state lab and clinical lab directors

## Slide 10: Work group 1’s scope, activities (2)
AR Electronic Laboratory Reporting (ELR) |  |  | 
# | Recommendation | Lead | Stakeholders
1 | Establish and disseminate best practices in ELR for AR by revisiting the guidance document created by the CSTE AR/ELR Working group in 2017 for CRE, (“Best Practices for Surveillance of Antimicrobial Resistance via Electronic Laboratory Reporting Recommendations from the CSTE AR/ELR Working Group, June 2017”), and broadening its scope to include the other pathogens and AR mechanisms that should be reported through ELR. | CSTE | CDC, CSTE, APHL, vendors, state lab and clinical lab directors
2 | All laboratories that submit reportable lab findings to public health via ELR should submit reportable AR laboratory findings via ELR, with messages conforming to nationally accepted standards, validated for accuracy and completeness of content and structure when sent or received. Laboratories that are not current reporting via ELR are encouraged to do so, especially as electronic reporting of AR is compelling reason to develop this capacity. | CDC (ELC) | CDC, CSTE, APHL, vendors, state lab and clinical lab directors
3 | ELR for laboratory results obtained through the AR Lab Network data should be submitted to public health agencies using HL7 messages routed through AIMS. | CDC (ARLN) and APHL | CDC, CSTE, APHL, state lab and clinical lab directors, state AR coordinators
Linking Laboratory and Epidemiological Data |  |  | 
1 | Publish guidelines on how to create and maintain linkages between laboratory findings and case findings for state, local and CDC programmatic needs. | CDC | APHL, CDC, CSTE, ARSTF

## Slide 11: Activity planning
Glorified “To Do” list with timeframes, “responsible person”
Key dates:
  Items for inclusion in CSTE Annual Conference Roundtable (if accepted) – by May 29
  CSTE Annual Conference Roundtable – by June 6
  Year 3 Report draft – by June 30
  Year 3 Report final – by July 31
Briefings about current status, opportunity for collaboration – Michael Waters, Steven Gitterman, FDA on SHIELD?
Contact CDC ELC regarding review copy of FOA, messaging related to AR in ELR during TA during the application process?
Presentation from CDC lab/ARLN on the issue of lab/epi linkage (e.g., accession #s)?
Other [Planning brainstorming]?

## Slide 12: Questions, discussion, next steps

## Slide 13: Contact information
Scott Troppy (Lead Member): scott.troppy@state.ma.us
Brooke Beaulieu (staff, CSTE): brooke@cste.org
Rich Melchreit (staff, CSTE): richmelchreit@gmail.com