ARSTF Work Group 5: Surveillance Scope

Call notes 2/14/19

10-11 am

Attendees:  Don Weiss, Chris Czaja, Janet Hindler, Brooke Beaulieu, Beaulieu, Rich Melchreit, Alex Daniels, DJ Shannon, Anne Haddad, Megin Nichols, Molly Kratz, Kenya Murray, Jackie Rueben, Nychie Dotson, Allison Brown, John Stelling, Scott Troppy, Joe Gerth, Matthew Burns, Sarah Schrum, Shaina Bernard

Note: Call-in users may not be fully captured

This was the inaugural call of the WG for orientation of members and initial planning.

- A slideshow was presented that gave a brief background bout the recommendations, the function of the WG, role and responsibilities of members of the Work Group, timeline and expected call schedule and call and work product logistics.  This Work Group has two recommendations to advance, 1) facilitating a dialog at CSTE about surveillance of non-clinical case (e.g., colonized) individuals with public health condition of public health importance, in particular antimicrobial resistance; and 2) promotion of state/big city cumulative antibiograms as a public health tool for AR surveillance and data for action.

- The anticipated outcomes to fulfill the WG’s charge to move the recommendations forward:

  - Colonization – as specified in the recommendation itself, production of a CSTE policy that can lead to position statement(s)

  - Antibiograms – a survey of states to assess needs, capacity, experience and status of statewide antibiograms, and needs for TA on setting up antibiograms and use of them; this would lead to guidance or a first draft of TA materials, possibly a Toolkit

- For both of the recommendations within this topic area (colonization, antibiograms), the group indicated we need to perform an assessment on state and local health department activities, capacity, and perspectives before developing a CSTE policy for colonization reporting, and for any guidance TA materials/toolkit for cumulative antibiograms for public health.  Surveys would be good tools for these two assessments.  The colonization assessment would benefit from clarifying terms and definitions.

- Developmental work to help inform the surveys:

  - Colonization – a call is being set up by WG staff with Rich Danila, CSTE ID Committee chair, as the possible facilitator, with individuals he suggests, some of whom would support and others have concerns about colonization reporting.  Likely he will suggest that Marion Kainer and Al DeMaria be on the call.  WG staff and Don Weiss, WG 5 Lead Member, will also likely be invited to be on the call.

  - The national level survey will be answered by HAI and AR Coordinators and perhaps state epis if they are heavily involved in AR, as some are (i.e., this is a state level assessment, as this is the audience for the TA).  However, states have done assessments within the state that can be useful background information to develop HAI/AR Coordinator questions about their experience and capacity to assess within their states as a step toward developing a statewide antibiogram. Members were encouraged to share any such in-state assessments they have done (e.g., Connecticut recently performed one), and any suggest they have for the questions for the HAI/AR Coordinators (the state-level assessment that CSTE will do at the WG’s request).  Review of the current CLIS M39, the “gold-standard “ guidance would be helpful.  Staff will attempt to get access to this guidance for WG members review (it has to be purchased).

  - In writing the survey we will need to determine whether it should be one survey instrument with two parts (Part 1: colonization; Part 2: antibiogram) or two separate surveys.  We may need to do two separate surveys as the expected survey respondents will likely be different (state Epis for colonization; HAI/AR Coordinators for antibiograms).

  - Staff and Work Group members will collaborate on writing the survey questions (staff do the bulk of the writing, survey distribution, follow-up to increase response rate, and data analysis).  WG members suggest questions, review and comment for editing, review data from assessments.

- Next steps:

  - Brooke will set up and send out recurring calendar 1 hour appointment for every other Thursday at 10:00 AM ET

  - Brooke will also set-up a workgroup Basecamp, to which all WG members will have access. Basecamp is essentially is a workspace where you can share documents, post resources, and chat about items. This will help us in communicating, making resources and references readily available, and sharing documents in development among group members for comment.

  - Rich and Brooke will post call materials, including minutes to review and CT’s antibiogram survey as a jumping off point for developing antibiogram survey questions on Basecamp.

  - Brooke will include a prompt in the follow-up email to send any preliminary thoughts on antibiogram survey questions by next week.

  - Brooke and Rich Melchreit will work with Don and Rich Danila to set up the consultation with him and some informants regarding colonization, to explore the issue and to inform next steps regarding a policy brief or statement.

  - Rich and Brooke will look into getting a copy of CLSI M39 for WG members to review.

  - Next call 2/28, 10-11 am