Agenda

| Time | Activity |
| --- | --- |
| 8:30 – 8:45 am | Welcome, Introductions, Workplan Review and Updates |
| 8:45 – 10:30 am | Metrics Refinement |
| 10:30 – 10:45 am | Break |
| 10:45– 12:00 pm | Metrics Refinement Cont. |
| 12:00 – 1:30 pm | Lunch (On your own) |
| 1:30 – 2:30 pm | Update workplan |
| 2:30 – 2:45 pm | Break/Adjourn |

# Evaluate DT Worksheet 2: Key Steps, Deadlines, Accountabilities

# Implementation Priority/Title: Evaluate the overall effectiveness of outbreak response

| ## Result [#1]: Preliminary Analysis of CIFOR Performance Measures (Ch 8) data reported to CMET |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |
| - Pass increasing reporting to CMET to PROMOTE DT and recommend metric of 8 or more total sites. | 9/27/16 | Scott |
| - Conduct preliminary analysis of Performance Measure data entered into C-MET on 7/1/17 | 9/1/17 | Craig |
| - Present results of preliminary analysis to CIFOR Council and 3rd Edition Revision WG | Sept 2017 (fall CIFOR meeting) | Craig |

| ## Result [#2]: Discrete list of metrics to evaluate outbreak response ## a. With specific metrics for individual multistate outbreak investigations |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |
| - Identify, gather, and summarize existing metrics data on outbreak response | 10/31/16 | Jessica H./Thuy |
| - Create list of key metrics to best evaluate outbreak response (based on #1) | 4/1/17 | Scott |
| - Recommend list of metrics for inclusion in Chapter 8 of 3rd edition of CIFOR Guidelines | 9/1/2017 | Scott |

| ## Result 3: Discrete lists of metrics to evaluate the influence of CIFOR on outbreak response and mechanisms to collect qualitative data and stories about outbreak response |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |
| - Identify, gather, and summarize existing sources of data on CIFOR influence. Examples: agencies who’ve used CIFOR toolkit (and evals), RRTs program improvement, web hits/downloads, C-MET uploads, books printed/delivered, CDC/FDA/FSIS programs using CIFOR performance measures, etc | 1/1/17 | Rachel and Thuy |
| - Create list of metrics to use to evaluate the influence of CIFOR | 2/1/17 | Rachel (coordinates Eval DT) |
| - Identify method(s) of eliciting additional quantitative and qualitative data about CIFOR’s influence | 1/15/17 | Scott and Don |
| - Implement methods identified in #6 | 11/30/16 - 5/1/17 | Elizabeth |

| Result #4: Framework established for after action report/hot washes for CIFOR council |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |
| - Identify, gather, and summarize existing after action report/hot wash procedures/templates | February 1, 2017 | Kirk and Travis |
| - Meet with CDC Outbreak Net Team, FDA CORE, FSIS | March 1, 2017 | Kirk |
| - Propose process/metrics to CIFOR Council | September 2017 | Kirk |