# CIFOR Worksheet 2: Key Steps, Deadlines, Accountabilities

# Implementation Priority/Title: Identify what is being done in the area of outbreak response and what needs to be improved

| Result 1: Address recognized gaps or implement best practices which if adequately addressed would improve foodborne outbreak response. |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |
| 1. Conduct brainstorming within identify team to identify gaps and best practices within identify team | April / May 2017 | Identify team |
| 2. Develop brief on each best practice / gap identified to share with appropriate team / agency | August 2017 | Identify team |
| 3. Advocate for teams/agencies to begin work to address | September 2017 | Identify team |
| 4. Review/update list every year | Ongoing | Identify team |

| Result 2: Identify three to five high priority gaps or best practices which if adequately addressed would improve foodborne outbreak response. |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |
| Compile gap analysis/findings from outbreak response completed by agencies/groups - PFP |  |  |
| Develop and implement a survey of CIFOR membership at different levels (federal, state, and local) to ID gaps and best practices based on experience/expertise |  |  |
| Conduct brainstorming sessions for gap and best practice identification within identify team |  | Identify team |
| Review CIFOR guidelines for gaps (*can utilize contractor findings if meet needs) |  |  |
| Review and prioritize identified gaps/ best practices from the various sources |  |  |
| Compile a report listing of high priority gaps to address through projects / future CIFOR revisions |  |  |

| Result 3: Review relevant CIFOR project proposals and CIFOR final projects which address gaps and best practices that fall within the scope of the identify team |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |
| Support FSIS project and review project results as needed, including: - Review/refine FSIS proposal - CIFOR membership reviews focus groups guides - Review report findings | 2017 2016 April 2017 September 2017 | Identity team |

Focus group notes – review focus group guides and get comments to Karen and Kristen by April 7th.

| Result 4: Identify practices that if appropriately implemented would prevent or reduce foodborne outbreaks from the pathogen-food pairings with the highest attributions fractions. (disease prevention) |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |
| Reach out to other groups working on this area to determine what work has already been done - Contact CDC, FDA, USDA and obtain attribution information around Salmonella and Campylobacter |  |  |
| IFSAC present on attribution data (Note: May need to consider emerging issues outside of pairings) |  |  |
| Identify which pathogen-food pairing to prioritize |  | Identify team |
| Obtain and review AAR with a disease prevention lens, including inviting key stakeholders to present on outbreaks |  | Identify team |
| Utilizing facilitative brainstorming session with members of the ID team, develop a list of practices or policies that may result in a reduction in foodborne outbreaks. (iterative process) - Identify best practices for universal adoption (e.g. certified food managers identified by EHS-Net) - Develop recommendations for CFP and other important stakeholders |  | Identify team |
| Present proposals to CIFOR Council for adoption as developed |  |  |
| Promote dissemination of IFSAC/Food Net source information |  |  |