# CIFOR Worksheet 2: Key Steps, Deadlines, Accountabilities

# Implementation Priority/Title: [Choose from the list below]

Identify what is being done in the area of outbreak response and what needs to be improved

Lead the development of new CIFOR products to address remaining gaps and barriers and align activities across partner organizations and programs

Promote model practices and other tools to support improvement

Evaluate the overall effectiveness of outbreak response

| ## Result 5: Identify current multidisciplinary foodborne outbreak training options |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |
| - Organize call(s) with IFPTI and COE training work group to hear about current multidisciplinary FBO training efforts | Summer 2017 | Kirsten Larson |
| - Summarize training options using Colorado COE list as a starting point - John Tilden- NCBRT information - Associations- current available training | September 30, 2017 | Robyn Atkinson Dunn John Tilden Monica McKenzie |

Result:  insert the result from Worksheet 1

Key Step: “how” – the few tactical actions required to achieve the result

Deadline: “when” – the date by which the step will be completed

Accountability: “who” – the person or group responsible for completing the step