# CIFOR Worksheet 2: Key Steps, Deadlines, Accountabilities

# Implementation Priority/Title: [Choose from the list below]

Identify what is being done in the area of outbreak response and what needs to be improved

Lead the development of new CIFOR products to address remaining gaps and barriers and align activities across partner organizations and programs

Promote model practices and other tools to support improvement

Evaluate the overall effectiveness of outbreak response

a.	Contract a consultant by December 31, 2016

b.	Identify structure and timeline for group

c.	Develop, administer and analyze CIFOR Guidelines needs assessment via a survey

- d.	Revision workgroups will be identified and convened in the next 12 months.

| ## Result 1: CIFOR guidelines revisions. |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |
| 1. Propose a structure for the CIFOR Guidelines Revision Work Group and present to Council | March 30, 2017 | TBD |
| 2. In collaboration with CSTE consultant, Lead DT Co-Chair will provide updates on Guidelines revision progress on Co-Chair development team calls | Monthly | Robyn Atkinson Dunn |
| 3. In collaboration with CSTE consultant, Lead DT Co-Chair will provide periodic updates on Guidelines revision progress to the Lead DT | Ad hoc | Robyn Atkinson Dunn |
| 4. In collaboration with CSTE consultant, the Lead DT will update the Council on Guidelines revisions progress as requested | Ad hoc | Lead DT member |

Result:  insert the result from Worksheet 1

Key Step: “how” – the few tactical actions required to achieve the result

Deadline: “when” – the date by which the step will be completed

Accountability: “who” – the person or group responsible for completing the step

# CIFOR Worksheet 2: Key Steps, Deadlines, Accountabilities

# Implementation Priority/Title: [Choose from the list below]

Identify what is being done in the area of outbreak response and what needs to be improved

Lead the development of new CIFOR products to address remaining gaps and barriers and align activities across partner organizations and programs

Promote model practices and other tools to support improvement

Evaluate the overall effectiveness of outbreak response

| ## Result [#]: [Insert Result Name] |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |

Result:  insert the result from Worksheet 1

Key Step: “how” – the few tactical actions required to achieve the result

Deadline: “when” – the date by which the step will be completed

Accountability: “who” – the person or group responsible for completing the step

# CIFOR Worksheet 2: Key Steps, Deadlines, Accountabilities

# Implementation Priority/Title: [Choose from the list below]

Identify what is being done in the area of outbreak response and what needs to be improved

Lead the development of new CIFOR products to address remaining gaps and barriers and align activities across partner organizations and programs

Promote model practices and other tools to support improvement

Evaluate the overall effectiveness of outbreak response

| ## Result [#]: [Insert Result Name] |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |

Result:  insert the result from Worksheet 1

Key Step: “how” – the few tactical actions required to achieve the result

Deadline: “when” – the date by which the step will be completed

Accountability: “who” – the person or group responsible for completing the step

# CIFOR Worksheet 2: Key Steps, Deadlines, Accountabilities

# Implementation Priority/Title: [Choose from the list below]

Identify what is being done in the area of outbreak response and what needs to be improved

Lead the development of new CIFOR products to address remaining gaps and barriers and align activities across partner organizations and programs

Promote model practices and other tools to support improvement

Evaluate the overall effectiveness of outbreak response

| ## Result [#]: [Insert Result Name] |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |

Result:  insert the result from Worksheet 1

Key Step: “how” – the few tactical actions required to achieve the result

Deadline: “when” – the date by which the step will be completed

Accountability: “who” – the person or group responsible for completing the step

# CIFOR Worksheet 2: Key Steps, Deadlines, Accountabilities

# Implementation Priority/Title: [Choose from the list below]

Identify what is being done in the area of outbreak response and what needs to be improved

Lead the development of new CIFOR products to address remaining gaps and barriers and align activities across partner organizations and programs

Promote model practices and other tools to support improvement

Evaluate the overall effectiveness of outbreak response

| ## Result [#]: [Insert Result Name] |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |

Result:  insert the result from Worksheet 1

Key Step: “how” – the few tactical actions required to achieve the result

Deadline: “when” – the date by which the step will be completed

Accountability: “who” – the person or group responsible for completing the step