Lead Development Team Call

Tuesday, March 21, 2017 @ 3:00 p.m. ET

Toll-free teleconference #: 1-866-640-2398

Passcode: 3525450

AGENDA

Goals- At the conclusion of this call, the Lead Development Team will:

- Finalize an in-person meeting agenda for Salt Lake City, March 29, 2017.

- Be aware of fellow development team (Lead, Promote, Evaluate) goings on

- Be up-to-date on the status of the Foodborne Illness Complaint Systems, OUE Guidelines Phase II and CIFOR apps.

- Review of action items/minutes from last call 12-15-16 (Kirsten)

  - Thuy and Dhara will pull questions from the RAND evaluation (of the CIFOR Guidelines) and put together a draft gaps analysis survey for the development team and work group to review.

    - Part of the consultant’s scope of work is conduct a gap analysis to determine what revisions are needed. The survey piece will likely be rolled in to that piece of the consultant’s work.

  - Please let CSTE know if you’re interested in volunteering for a CIFOR Guidelines work group that will aid a consultant on the overall revision process and address revisions and comments on the full draft document once available. Current volunteers include Robyn Atkinson Dunn, Don Sharp and Carlota Medus.

    - Please fill out survey that Thuy sent out on <<insert date>> so CSTE can set up a more formal listserv.

  - CSTE will provide a list of project proposals from the past few years and update the status on projects as appropriate.

    - Circulated list of project proposals a while back, and happy to recirculate to determine if there are any outstanding projects worth revisiting. Haven’t been many new project proposals in the past year.

    - Dhara and Thuy will recirculate with this group prior to the in-person meeting.

- Review, discuss and finalize an in-person meeting agenda (Robyn)

  - Please refer to the draft in-person meeting agenda

- Other team updates/ goings on

  - Identify/ Evaluate Teams (Thuy/ Dhara)

    - Evaluate-

      - Identifying a process, tool, etc. for evaluating individual outbreaks. Are folks investigating them the way we want them to or do we need additional guidelines

      - Root cause is a separate issue being addressed by Identify DT (e.g. preventive measures and interventions to prevent Delmarva tomato Salmonella outbreaks moving forward, etc.)

  - Promote Team (Don)

    - Suggests that DT Co-Chairs meet from 4:30-5:00 p.m. on 3-29 to regroup before the rest of the meeting.

    - Linette Granen (APHL) put together a draft CIFOR Marketing Plan that will eventually be available for review and comment.

- Project updates

  - Foodborne Illness Complaint Systems (Thuy)

    - Craig Hedberg will participate in the Evaluate Development Team and CIFOR Council meeting next week and will be present on the FICS project on Friday during the business meeting.

  - CIFOR app (Thuy)

    - RFP out by the end of this week. Have had several internal IT discussion to identify potential vendors and needs for the projects, etc.

  - OUE Guidelines Phase II (Kirsten)

- CIFOR Guidelines Revision (Thuy)

  - Next steps

    - Should have RFP out for consultant by end of this week, and hope to have consultant on board by end of April

  - Current needs