# CIFOR Worksheet 2: Key Steps, Deadlines, Accountabilities

# Implementation Priority/Title: Promote model practices and other tools to support improvement

- Increased use of CIFOR products by front line public health workers

- Increased recognition of CIFOR materials as the standard of practice by decision makers

| Result 1:Redesigned CIFOR website |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |
| - Gather feedback on existing mock-up of redesign and incorporate feedback | October 2016 | Amy/Anastasia |
| - Gather feedback on 1st draft of new design actual site itself and incorporate feedback | Mid November 2016 | Amy/Anastasia |
| - Assess and Revise Clearinghouse content and devise new format – crosswalk with CDC COE data | Beginning of November 2016 | Amy/Anastasia and Promote DT members |
| - Begin usability testing by target audience | Beginning of December 2016 | Amy/Anastasia |
| - Evaluate end user feedback and make necessary changes | December 2016 | Promote DT and other Council members |
| - Website redesign complete | December 2016 | NACCHO contract |

| ## Result 2: Completed CIFOR Marketing Strategy and Implementation Plan |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |
| - Hold a scoping meeting with Association/Agency marketing staff to define what a CIFOR Marketing Plan will include | February 2017 | Shari |
| - Report on scoping meeting | March 2017 | Shari/NACCHO |
| - Finalize RFP(s) for professional marketing assistance | June 2017 | Elizabeth |
| - Identify funds and transfer to association(s) | August 2017 | Governance Council |
| - Hire consultant(s) and approve work plan(s) | September 2017 | Funded Association(s) |

| ## Result 3: Increased use of the C-MET |  |  |
| --- | --- | --- |
| ## Key Step | ## Deadline | ## Accountability |
| - Build flyer template to meet current needs for external marketing | December 2016 | Anastasia |
| - Create CIFOR image library | Start now, build contents by March 2017 | CSTE |
| - Create interim flyers for new and recent products | December 2016 | Anastasia |
| - Revise templates based on new branding scheme that may come out of Marketing Strategy | September 2017 | NACCHO and Promote DT |
| - Increase data input into C-MET by at least 10 users | September 2017 | Kirsten Larson |