# CIFOR Worksheet 1: Results and Metrics

# Implementation Priority/Title:  Promote model practices and other tools to support improvement

  - Increased use of CIFOR products by front line public health workers

  - Increased recognition of CIFOR materials as the standard of practice by decision makers

| ## Result | ## Metric | ## Status 9/1/17 |
| --- | --- | --- |
| - Redesigned CIFOR website | December 2016 | NACCHO will provide update at Denver meeting |
| - Completed CIFOR Marketing Strategy and Implementation Plan | Marketing plan approved by the Council by September 30, 2017 | Moving along, have divided into sub-groups to move the initial projects forward, updates to the marketing plan are currently in process |
| - Increased use of the C-MET | An additional 10 jurisdictions will have entered their data into C-MET by September 30, 2017 | Promote team was advised we should promote this. Will include this in our September 2017 Promote Team call agenda items |

Implementation Priority/Title: the name of the implementation priority/track of work with its associated strategic map objectives

Result: “what” – a specific outcome to be achieved in support of the track of work/objectives (generally limited to three to five results)

Metric: “how well/how much/etc.” – a measure or indicator of whether the result was achieved. The four typical types of measure are quality, quantity, cost and time.