## CIFOR Promotion Plan
Timeline | Product | Objective | Action Item(s) | Outcomes/Metrics | POC
January 2018
Jan 5 | General | CIFOR Members to update their websites | Internal only | All member sites updated, | Shari
Jan 11 | CIFOR & Clearinghouse | Promote orgs updated website, plug Clearinghouse | Tweets, social media posts , e-news | Increased website views
Jan 18 | Guidelines | Guidelines Revision Meeting | Tweets, re-tweet
Jan 27 | Industry Guidelines | Promote Ind Guidelines | Ask Lisa to talk w/ Industry workgroup |  | Lisa
February
Feb 9 | CIFOR (combine w/below)wait for Amy | Highlight Testimonials | Tweet portion of a testimonial, then direct back to CIFOR website
Feb 16 | Toolkit | Promote use of Toolkit
Feb 23 | Law Project | Promote Law docs | Tweets, SM, e-news, #ciforfood
March
March 15 | CIFOR Council Meeting | Mass promotion of CIFOR | Tweets, SM |  | All
March 27 | Industry Guidelines | GMA Science Forum | Re-tweet and promote CIFOR, provide talking points/messages to GMA contacts
March 29 | Law docs | CDC's Public Health Law Program | Blurb | Distributed via CDC's Listserv
April
April 16 | CIFOR/All | CFP, Richmond, VA | If attending tweet & have orgs re-tweet, use CFP hashtag |  | Andre & Ernie
April 17 | CIFOR/All | NACCHO Preparedness Summitt | NACCHO will have Guidelines and materials at booth | Promotion at National conference | Amy & Michele
May
May 7-10 | Industry Guidelines | Food Safety Summit | Industry workgroup to promote |  | Lisa/Frank Ferko
May 19 | Industry Guidelines | NRA, Chicago | Industry workgroup to promote |  | Lisa
May 20 | Coming Soon New Guidelines | Teaser on new Guidelines | Promote via SM and e-news
June
June 2 | All | APHL Conf, Pasadena, CA |  |  | Shari
June 9 | All | AFDO Conf, Burlington, VT |  |  | Lisa
June 10 | All | CSTE Conf, West Palm Beach, FL |  |  | Thuy
June 25 | All | NEHA Conf, Anaheim, CA |  |  | Elizabeth
July
July 10 | All | NACCHO Conf-New Orleans |  |  | Amy
August
mid-August | CIFOR | Short CIFOR Overview Video | Promote via SM and e-news
August 26 |  | ICEID | Shari will take flyers and put out on tables, Thuy will bring for the reception
September
Food Safety Education Month
| CIFOR-All products | New content on website - Long overview video
October
Oct 4 | Law Project | PH Law Conference
Oct 9-11 | Industry Guidelines | NRA Food Safety & Quality Assurance executive study group conference | On agenda to present? |  | Lisa/John Zimmermann
November
Nov 14-15 | CIFOR Council & Guidelines | In-Person Omaha meeting | Social media push during meeting
December
| Promote CIFOR | CDC Holiday Tweeter Chat | Beth
January 2019
Jan 15-17 |  | PN/OBN Tampa, FL booth
Febuary 2019
Feb 5-8 |  | PN/OBN San Diego, CA booth
Feb 26 |  | Mid-Continental Association of Food & Drug Officials (MCAFDO) | Scott Holmes
| Industry Guidelines | Promote to non-CIFOR, boots on ground | Andre, Christina, Michele
March 2019
March 5-8 |  | PN/OBN Omaha, NE booth
March 26-29 |  | NACCHO Preparedness Summit, St. Louis
April 2019
| Complaint Systems Guidelines | a resource | Beth will help work on it
May 2019
June 2019
June 22-26 |  | AFDO Conference, Buck Head, GA
June 12-14 |  | GA EHA conference
June 2-6 |  | CSTE Conference, Raleigh, NC
June 2-6 |  | APHL St. Louis
July 2019
July 9-12 |  | NEHA Conference, Nashville, TN
July 9-11 |  | NACCHO Conference, Orlando, FL
August 2019
Start developing 3rd Edition
FDA retail food seminars
2018-04-11 |  | MFRP Alliance / Lab Accred, Houston, TX
|  | IAFP - July 21-24, Louiseville, KY | Abstacts open now - Lisa
|  | Region 4 NEHA | Abtracts open now - Scott
Food Safety Summit
Industry conferences ??
North Carolina EHA - Sept 2019
CFP 2020 in Denver - Booth & Present

## Product Info
Product | CIFOR Target Audience | Other Groups? | Elevator Pitch
Guidelines | All | who are we missing?? Do another time | Pull from Shari's messages
Industry Guidelines
OUE Guidelines
Law Projects
General CIFOR Promotion
Website
Clearinghouse | promote featured tool quarterly, and use of clearinghouse |  | NACCHO will tell us when up to date
C-MET
How to promote products?
Conduct Webinars
Flier/Handout
Promote at Conferences/Meetings
Social media posts (list all)
Association/Agency e-news
Association/Agency website