## CORHA Activities At-A-Glance

Green = Completed; Yellow = In Progress; Red = Not Started; Blue = Ongoing

| Activities | Status | Completed/Expected | Notes |
| --- | --- | --- | --- |
| A: Detection and Reporting |  |  |  |
| Outbreak Definitions |  |  |  |
| Candida auris |  | Q2 2018 | Completed; Pending review process |
| Clostridium difficile |  | Q2 2018 | In progress |
| CRE |  | Q2 2018 | Completed; Under review |
| MDRO Gram Negatives |  | TBD |  |
| NTM (extra-pulmonary) |  | Q2 2018 | In progress |
| Scabies |  | Q4 2017 | Available on the CORHA website |
| Assessment to Healthcare Facilities |  | Q3 2018 | Distributed through SHEA and APIC channels |
| Assessment to Public Health |  | Q4 2017 | Completed; Analysis in progress |
| A4: Laboratory |  |  |  |
| Workgroup charge |  | Q1 2018 | Finalized |
| Workgroup member identification |  | Q3 2018 | Workgroup lead identified |
| A5: Policy |  |  |  |
| Workgroup charge |  | Q2 2018 | Finalized |
| Workgroup member identification |  | Q3 2018 |  |
| B: Investigation and Control |  |  |  |
| Response Activity Tracking System |  | Q4 2017 | Available on the CORHA Website |
| Sample Tracking System Data Dictionary |  | Q4 2017 | Available on the CORHA Website |
| Candida auris |  | Q3 2018 | Completed; Pending review process |
| Clostridium difficile |  | Q3 2018 | Near completion; Awaiting WG A product |
| CRE |  | Q4 2018 |  |
| AB6: External Resource Reviews (Inv and Control) |  |  |  |
| Candida auris |  | Q3 2018 |  |
| Clostridium difficile |  | Q3 2018 |  |
| CRE |  | Q2 2018 | In progress |
| MDRO Gram Negatives |  | TBD |  |
| NTM (extra-pulmonary) |  | TBD |  |
| Scabies |  | Q1 2018 | Pending final round of SME reviews |
| ABCD: High-Level Guidance |  |  |  |
| Chapter 3: Planning and Preparation for HAI/AR Outbreak Response |  | Q3 2018 | In development |
| Chapter 4: HAI/AR Outbreak Detection and Reporting |  | Q4 2018 | In development (outline stage) |
| Chapter 5: Investigation of HAI/AR Outbreaks |  | Q2 2018 | Pending review process |
| CD: Communications and Marketing |  |  |  |
| CORHA Website |  |  | Website live; Ongoing |
| CORHA Branding |  |  | Materials developed; Ongoing |
| CORHA Outreach and Promotion |  |  | Ongoing |