[bookmark: _Toc514423563]CORHA Activities At-A-Glance
Green = Completed; Yellow = In Progress; Red = Not Started; Blue = Ongoing
	Activities
	Status 
	Completed/Expected
	Notes

	A: Detection and Reporting
	 
	 
	 

	Outbreak Definitions
	
	
	

	Candida auris
	
	Q2 2018
	Completed; Pending review process

	Clostridium difficile
	 
	Q2 2018
	In progress

	CRE
	 
	Q2 2018
	Completed; Under review 

	MDRO Gram Negatives
	 
	TBD
	

	NTM (extra-pulmonary)
	 
	Q2 2018
	In progress

	Scabies
	 
	Q4 2017
	Available on the CORHA website

	Assessment to Healthcare Facilities
	 
	Q3 2018
	Distributed through SHEA and APIC channels

	Assessment to Public Health
	 
	Q4 2017
	Completed; Analysis in progress

	A4: Laboratory 
	 
	 
	 

	Workgroup charge 
	 
	Q1 2018
	Finalized 

	Workgroup member identification 
	 
	Q3 2018
	Workgroup lead identified

	A5: Policy 
	 
	 
	 

	Workgroup charge 
	 
	Q2 2018
	Finalized

	Workgroup member identification 
	 
	Q3 2018
	

	B: Investigation and Control
	 
	 
	 

	Response Activity Tracking System
	 
	Q4 2017
	Available on the CORHA Website

	Sample Tracking System Data Dictionary
	 
	Q4 2017
	Available on the CORHA Website

	Candida auris
	 
	Q3 2018
	Completed; Pending review process

	Clostridium difficile
	 
	Q3 2018
	Near completion; Awaiting WG A product

	CRE
	 
	Q4 2018
	

	AB6: External Resource Reviews (Inv and Control)
	 
	 
	 

	Candida auris
	 
	Q3 2018
	

	Clostridium difficile
	 
	Q3 2018
	

	CRE
	 
	Q2 2018
	In progress

	MDRO Gram Negatives
	 
	TBD
	

	NTM (extra-pulmonary)
	 
	TBD
	

	Scabies
	 
	Q1 2018
	Pending final round of SME reviews

	ABCD: High-Level Guidance
	 
	 
	 

	Chapter 3: Planning and Preparation for HAI/AR Outbreak Response
	
	Q3 2018
	In development

	Chapter 4: HAI/AR Outbreak Detection and Reporting
	 
	Q4 2018
	In development (outline stage)

	Chapter 5: Investigation of HAI/AR Outbreaks
	
	Q2 2018
	Pending review process 

	CD: Communications and Marketing
	 
	 
	 

	CORHA Website
	 
	 
	Website live; Ongoing

	CORHA Branding
	 
	 
	Materials developed; Ongoing

	CORHA Outreach and Promotion
	 
	 
	Ongoing
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