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Product Details
	Product
	Workgroup
	Status
	Publish deadline 
	Notes

	C. auris
	Workgroup A and B
	Final draft published

	August 2021

	-The WG B section of the product was GC-approved with minor comments on 08/28/2019
 -The WG B section of the product was sent to Council for review and vote by CSTE on 10/17/2019
- The WG B section of the product was Council-approved in October 2019
- The WG A/B combined product is with the Technical Editor
-Product received from the Technical Editor in July 2021. Comments were reviewed by staff and final draft published to the website. 


	CDI 

	Workgroup A and B
	Final draft published 
	January 2021 

	- The WG B section of the product was Council-approved in November 2018
- The WG B section of the product was revised in the Spring-Summer of 2019
- The WG B section of the product was GC (re)approved on 08/28/2019
- The WG B section of the product was sent to the Technical Editor in September 2019
- The WG A and B combined draft was completed in March 2020
- The WG A and B combined draft was sent to the Technical Editor in June 2020
- Received technical edits, which were reviewed and cleared by Joe in January 2021. Pending website posting.
- Product was Council-approved in December 2020 and posted to the website in January 2021.

	CRE

	Workgroup A and B
	Product received from the Technical Editor in July 2021, pending workgroup lead review.
	September 20, 2021  
	- The completed and combined A/B draft was sent to the Technical Editor in August 2019. 
- The WG A section of the product was Council-approved and posted to the website on 09/05/2019
- The WG B section of the product was GC-approved with minor comments on 8/28/2019 
- The WG B section of the draft was sent for Council review and vote on 10/17/2019
- The WG B section of the draft was Council-approved in October 2019
- Comments from SHEA were addressed by WG B
- Product received from the Technical Editor in July 2021, pending workgroup lead review 


	Influenza
	Ad-hoc
	Final draft published 
	May 2021
	-Currently in development
-The ad hoc workgroup began working on a flu + COVID outbreak product on 09/18/2020
- Product was posted to the website in May 2021


	NTM
	Workgroup A and B 
	Product received from the Technical Editor in July 2021, pending workgroup lead review
	September 20, 2021 
	- The WG A section of the product was sent to the Technical Editor in August 2019
- An interim draft of the WG A section was posted to the CORHA website on 09/05/2019
- The WG A and B combined draft was completed in March 2020
- The combined product was sent to the Technical Editor in June 2020
- The combined product was approved by the Council in December 2020.
-Product received from the Technical Editor in July 2021, pending workgroup lead review 

	Group A Strep

	Workgroup A
	Currently in development 
	TBD 
	-Currently in development

	Medical Devices and Products
	Workgroup A
	The product is with CDC Isaac Benowitz for final SME review. This product will be tied into Supplement A of the P&P.
	November 2021 
	- Currently in development 
- The product is with CDC Isaac Benowitz for final SME review


	Medical Product-Related Assessment
	Workgroup B
	Checking with Puja, will update once confirmed 
	
	- Council-approved in May 2019
- The product was sent to the Technical Editor in August 2019
- An interim draft was posted to the CORHA website in August 2019
 

	HAI Outbreak Notification Framework
	Policy
	-Product received from the Technical Editor in July 2021, pending workgroup lead review
	September 20, 2021 
	-The product was sent to the Governance Committee on 1/17/2020
-The product was approved by half of the Governance Committee on 2/14/2020
-The product was approved by all GC members in April 2020
-An interim draft was posted to the CORHA website on 4/23/2020
-Minor updates and revisions were made to the product in June 2020
-The product was sent to the Technical Editor in June 2020. Pending review.
- The product was Council-approved in December 2020 and posted to the website in January 2021.
- Pending Technical Review
-Product received from the Technical Editor in July 2021, pending workgroup lead review 
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