CORHA Product Tracker 08/26/2021

# CORHA Product Tracker

Product Details

| Product | Workgroup | Status | Publish deadline | Notes |
| --- | --- | --- | --- | --- |
| C. auris | Workgroup A and B | Final draft published | August 2021 | -The WG B section of the product was GC-approved with minor comments on 08/28/2019 -The WG B section of the product was sent to Council for review and vote by CSTE on 10/17/2019 - The WG B section of the product was Council-approved in October 2019 - The WG A/B combined product is with the Technical Editor -Product received from the Technical Editor in July 2021. Comments were reviewed by staff and final draft published to the website. |
| CDI | Workgroup A and B | Final draft published | January 2021 | - The WG B section of the product was Council-approved in November 2018 - The WG B section of the product was revised in the Spring-Summer of 2019 - The WG B section of the product was GC (re)approved on 08/28/2019 - The WG B section of the product was sent to the Technical Editor in September 2019 - The WG A and B combined draft was completed in March 2020 - The WG A and B combined draft was sent to the Technical Editor in June 2020 - Received technical edits, which were reviewed and cleared by Joe in January 2021. Pending website posting. - Product was Council-approved in December 2020 and posted to the website in January 2021. |
| CRE | Workgroup A and B | Product received from the Technical Editor in July 2021, pending workgroup lead review. | September 20, 2021 | - The completed and combined A/B draft was sent to the Technical Editor in August 2019. - The WG A section of the product was Council-approved and posted to the website on 09/05/2019 - The WG B section of the product was GC-approved with minor comments on 8/28/2019 - The WG B section of the draft was sent for Council review and vote on 10/17/2019 - The WG B section of the draft was Council-approved in October 2019 - Comments from SHEA were addressed by WG B - Product received from the Technical Editor in July 2021, pending workgroup lead review |
| Influenza | Ad-hoc | Final draft published | May 2021 | -Currently in development -The ad hoc workgroup began working on a flu + COVID outbreak product on 09/18/2020 - Product was posted to the website in May 2021 |
| NTM | Workgroup A and B | Product received from the Technical Editor in July 2021, pending workgroup lead review | September 20, 2021 | - The WG A section of the product was sent to the Technical Editor in August 2019 - An interim draft of the WG A section was posted to the CORHA website on 09/05/2019 - The WG A and B combined draft was completed in March 2020 - The combined product was sent to the Technical Editor in June 2020 - The combined product was approved by the Council in December 2020. -Product received from the Technical Editor in July 2021, pending workgroup lead review |
| Group A Strep | Workgroup A | Currently in development | TBD | -Currently in development |
| Medical Devices and Products | Workgroup A | The product is with CDC Isaac Benowitz for final SME review. This product will be tied into Supplement A of the P&P. | November 2021 | - Currently in development - The product is with CDC Isaac Benowitz for final SME review |
| Medical Product-Related Assessment | Workgroup B | Checking with Puja, will update once confirmed |  | - Council-approved in May 2019 - The product was sent to the Technical Editor in August 2019 - An interim draft was posted to the CORHA website in August 2019 |
| HAI Outbreak Notification Framework | Policy | -Product received from the Technical Editor in July 2021, pending workgroup lead review | September 20, 2021 | -The product was sent to the Governance Committee on 1/17/2020 -The product was approved by half of the Governance Committee on 2/14/2020 -The product was approved by all GC members in April 2020 -An interim draft was posted to the CORHA website on 4/23/2020 -Minor updates and revisions were made to the product in June 2020 -The product was sent to the Technical Editor in June 2020. Pending review. - The product was Council-approved in December 2020 and posted to the website in January 2021. - Pending Technical Review -Product received from the Technical Editor in July 2021, pending workgroup lead review |