Workgroup A:  Outbreak Detection and Reporting

Timeline

Version: November 18, 2016

| Strategic Map Position | Project Goal | Action Items | Responsible Party | Deadline |
| --- | --- | --- | --- | --- |
| N/A | Miscellaneous | Schedule standing Workgroup A calls twice per month or every other week (Doodle poll) | Nicole (CSTE) | November 30, 2016 |
|  |  | Identify vice-chair (vice-lead? ) via email | Nicole (CSTE) | November 30, 2016 |
|  |  | Add additional representation - 1 additional permanent state HD representative (from non-EIP, less-resourced state) - 1 additional state HD representative ad hoc for completion of table - 1 additional APIC or SHEA representative with possible PH experience (Rachel Stricoff) - 1 additional permanent NACCHO member representative | Nicole (CSTE) – survey for state HDs, reach out to Rachel Stricoff Lily (NACCHO) – NACCHO member rep | January 15, 2017 |
|  |  | Add ALRN representative observer | Kathy (CDC) | December 1, 2016 |
| A1/A2 | Table draft | Update table shell - “Onesies” (e.g., 1 case associated with scope use) - Add scabies (note 1 case crusted scabies might be threshold) - Delete other bacteria | Wendy (CO) | December 15, 2016 |
|  |  | Divide table among workgroup members – assign 1-3 conditions, conditions will have 2 persons assigned (for purposes of populating table) | Wendy (CO) and workgroup | January 15, 2017 |
|  |  | Populate table draft (workgroup members working individually) | Assigned workgroup members | January 31, 2017 (at least 2 conditions – suggest deadline sooner for workgroup members already part of group); February 15, 2017 (other conditions – suggest later deadline for new workgroup members to allow them to catch up) |
|  |  | Ongoing review draft of populated table - On workgroup calls Prioritize CRE and C diff first, so we can coordinate with reporting requirement scan | Workgroup | Draft complete by April 30, 2017 |
|  |  | - Obtain feedback from entire CORHA group | Wendy (CO, to spearhead this) | Either separate call with CORHA, or at spring meeting - TBD |
|  |  | Obtain feedback from outside partners, to be determined | TBD | Following CORHA review - TBD |
|  |  | Preliminary scan of state reporting requirements for the purpose of developing questions - CRE and C diff reporting requirements for all states (as this is simpler to identify) C diff outbreak (which might be general outbreak reporting) for a group of selected states (as this will be more challenging) | Alexa (CDC) | December 1, 2016 |
|  | Scan of reporting requirements by state | - Define reporting requirements | Workgroup | December 1, 2016 |
|  |  | Determine format for output of scan | Workgroup | December 15, 2016 |
|  |  | Develop questions for state HD survey | Alexa (CDC) and workgroup | December 31, 2016 |
|  |  | Send survey to state HDs (coordinate with other survey questions below) | Nicole (CSTE) | Mid-February, 2017 |
|  |  | Analysis of survey results, report of survey results and scan | Nicole (CSTE, survey results), Alexa (CDC, scan) | Prior to spring meeting – TBD |
|  |  | TBD | TBD | November 18, 2017 (1-year goal) |
|  | Comparison of table (ideal state) with scan of reporting requirements (reality) – gap assessment | Gather preliminary background information on what is currently being done in this area - Susan Huang - Martin Cordoff (sp?) Epi Centers | Ryan (CDC) | December 31, 2016 |
| A3 | Scan to determine how using surveillance data to detect outbreaks (acute care facilities) | Develop methodology to gather more information systematically; could involve the following; - Survey of acute care facilities (would include question development, sending survey) - Focus groups - Posting on organizational boards (e.g., SHEA, APIC) | Workgroup | January 30, 2016 |
|  |  | - Apply methodology | APIC/SHEA representative? | TBD |
|  |  | Determine format for report (might include table of reporting systems and tools already available) | Workgroup | January 15, 2017 |
|  | Scan to determine how using surveillance data to detect outbreaks (public health agencies) | Develop questions for survey and obtain input on CSTE HAI Subcommittee call (January 24, 2017) | Marion (TN) | January 31, 2017 |
|  |  | Send survey to state HDs (coordinate with other survey questions above) | Nicole (CSTE) | Mid-February, 2017 |
|  |  | Analysis and report of survey results | Nicole (CSTE, analysis and results) | Prior to spring meeting – TBD |
|  |  | TBD | TBD | November 18, 2017 (1-year goal) |
|  | Develop at least one tool to be used to identify outbreaks from surveillance data (e.g., SAS code) – apply results of scan |  |  |  |