CORHA Workgroup B Call

Friday, 3:00-4:00 p.m. ET, February 15th 2019 (3rd Friday of every month)

Call Information:

Dial-in Number: (267) 930-4000
Participant Code:100-090-937#

Attendees:

Martha Ngoh (ASTHO)

Joe Perz (CDC)

Matt Crist (CDC)

Waleed Javaid (SHEA)

Steven Franklin (CDC)

Erin Epson (CA)

Matt Crist (CDC)

Elizabeth Mothershed (CDC)

Monica Schroeder (CSTE)

Puja Shah (CSTE)

Agenda:

- Introduce Puja Shah, new CSTE Staff Lead for CORHA activities

- Update on WGA / WGB co-lead discussion & priorities

  - WGA/WGB calls need coordination efforts for project priorities

    - Quarterly calls between co-leads on product discussion/updates

- Quick review of product status:

  - C diff

    - Matt & Joe to revise some outstanding language based on updated guidance released by CDC in December —reach out to Nimale Stone for final review

    - Once content finalized send to CSTE to assist with formatting & references

    - Send final version to Martha to share with GC and determine whether needs a re-vote by Governance

    - Steven will be working with C. diff SMEs to organize & vet resources and

  - CRE

    - CSTE (Monica) uploaded most recent version from in-person meeting onto Basecamp https://3.basecamp.com/3164497/buckets/1313556/uploads/1053476134

    - Erin will be lead for this product (with Joe and Waleed’s help)

    - Lab and surveillance are two separate parts. May be helpful to give a highlight about how to arrive at thresholds.

    - Plan to share revised draft next month (March call)

3. C auris Discussion  Finalization

  - Two versions of this document are attached for reference. One contains all edits in tracked changes, the second is a clean version.

  - Joe will coordinate

  - Allow lab workgroup (Kelly & Jafar - APHL) chance to review after next iteration

  - Edits for consideration:

    - Pulling out #3 footnote in Thresholds table and place under Points for Consideration

    - For 3.1 – maybe should have more about case finding / surveillance, and lab information included further up in document

    - Move 3.5 (case review) into 3.1

    - In 3.5 include “exposure to facility or other exposure outside the US…”, with reference to 3.3 (see section 3.3)

      - Could be offensive, change to “..e.g., exposure to high risk facilities with known C. auris transmission…”

    - Section 3.6 – streamline, if suggesting screening all patients consider including language such like ‘at minimum screen roommates’

      - May eliminate bullet b.

- Medical Device Discussion  Finalization

  - Current version attached

    - Includes revisions from Isaac based on discussions at in-person meeting in November, feedback from Dawn, and FDA edits

  - Undergoing pre-clearance review at FDA

  - Would like to present at APIC in June – Julie and Isaac presenting on medical device at APIC in June and would like to

  - Solicit review from WG B (2 week review period) before moving forward – big issues (errors and omissions)

Action Items:

- Joe and Matt to reach out to—Nimale Stone for CDI product final review

  - Joe to follow up on outstanding language

  - Matt Christ to incorporate edits regarding CDC CDI guideline released in December

- Steven to work with CDI SMEs to organize resources and vetted

- Erin to lead CRE product revisions with Joe and Waleed

  - Anticipated draft by March 26th call

- One more iteration on C. auris product before sending out to Lab group

  - Joe, Stephanie, Erin, Mary Alice, Snigdha

- Joe to keep WG B updated on FDA pre-clearance

- CSTE (Puja/Monica) to solicit final review on Medical Product Investigations Principles draft—to WG B