CORHA

Workgroup A: Detection and Reporting

Agenda

May 17, 2017

- Roll call

  - CDC – Steven Franklin

  - CSTE/States – Nicole Bryan, Jessica Helms, Wendy Bamberg, Andrea Flinchum, Maureen Tierney

  - NACCHO/LPHAs – Erin Laird, Stephanie Black

  - ASTHO – Elizabeth Ruebush

  - SHEA -

  - APIC – Linda Greene

- Quick regroup on workgroup members

  - Update workgroup members on email calendar item (correct Lilly, add Steven and Maroya, remove Ryan)

- Updates: Review progress at working group sessions of in-person CORHA meeting

  - CRE – working table – one more call to discuss and finalize – call on May 31

    - Maureen and Maroya to discuss before May 31

  - NTM – definition of NTM in nonpulmonary site - needs to be reported

    - What is the threshold for additional investigation?

      - If a pt had a recent surgery or if surgical hx, facility would want to investigate

    - Linda and MaryAlice not available June 14, Wendy will check with Kiran from CDC to make sure she can join this call – plan for July 12

  - Candida auris

    - MaryAlice and Stephanie to revise this – review in combination with another condition

  - Finalize survey questions – coordinate with workgroup B – Wendy to reach out to Waleed to discuss

  - Coordination with Workgroup B

- Review proposed tentative schedule (discuss where to add in survey to ACH/PH and scan of reporting requirements)

May 31:  CRE; finalize survey for ACH/PH?

June 14:

June 28:  C. auris (pending MaryAlice’s availability);  C. difficile?

July 12:  plan for NTM (pending Kiran’s availability)  Linda to lead call

July 26:  Complete or revisit any incomplete conditions; discuss scan of reporting requirements?  Linda to lead call

August 9: Scabies (no CDC SME on scabies – Steven will check with the team)

August 23:  MDRO Gram Negatives

September 6:  Singletons and conditions to be reported regardless of pathogens (e.g., case related to scope, product contamination, etc.)

- Action items and assignments

Framework for Workgroup A Plan

A1/A2: Developing outbreak definitions (A1/A2)

  - Creating pathogen-specific outbreak definitions (table shell)

    - Conditions: CRE, MDRO Gram negatives, NTM, C. auris, C difficile, Scabies

    - “Onesies”: Conditions that should be reported regardless of pathogen (e.g., related to scopes, product contamination)

    - Cross-cutting issues: Developing guidelines for determining baseline

  - Scan of reporting requirements for HAI outbreaks by state

  - Comparison of table (ideal state) with scan of reporting requirements

A3: Using surveillance data to detect outbreaks (A3)

  - Determining how surveillance data is used to detect outbreaks in PH and acute care facilities (survey)

  - Developing a tool to use to identify outbreaks from surveillance data