Kentucky HAI Prevention Program

Outbreak Investigation Guide

Notification

- Healthcare Associated Infections (HAI) Prevention Program staff fields initial call and collects as much of the following as possible:

  - Facility ICP personnel contact information for further correspondence

  - Number of cases

  - Timelines (admission, culture, discharge date and status)

  - Locations on facility (unit, room number)

  - Lab results (i.e., organisms) and other pertinent lab information (ex. resistance patterns, specimen source, further tests being performed, number of positive isolates by week or month for the last 6 months, etc.)

Meets outbreak definition

- CRE

- VRE

- MRSA

- MDRP

- MDRA

- ESBL

- C. diff

- Establish a case definition

Leadership

- Designate one IP nurse and one epidemiologist to serve as leads for the investigation. If one person is out of the office, the other will have all of the information. One of these two can be at the helm.

- Team involvement can vary based on availability/workloads/concurrent investigations/etc.

Communication

- Upon notification, the following shall be informed:

  - Reportable disease – obtain outbreak number

  - Infection Disease Section Chief

  - Division of Epidemiology and Health Planning Director

  - Appropriate LHD personnel

Variation

- Do we need to leave room for variability in approach by organism and by type of facility (e.g., CRE outbreak versus MRSA or ACH versus LTCF)?

Hypothesize

- Set a hypothesis to help guide the investigation. Will likely be dynamic.

Action items

- Collect EPID-250s on positive cases (will this become obsolete?)

- Advise surveillance cultures (under what circumstances)

- Arrange site visit

  - Infection control:

    - Observation of the environment

    - Observation of patient care

    - ICAR assessment?

  - Epidemiology (at a minimum assess the following):

    - Potential for a contaminated piece of equipment (e.g., a single scope or bottle of multi-use ultrasound gel)

    - Procedures/surgeries

    - Diagnoses of case-patients  and location from which they were admitted

    - Map of unit

    - And then maybe other stuff (comorbidities, antibiotics, previous healthcare exposures, staff contacts, etc.) would only be collected if the outbreak was “escalated” for some reason (e.g., rare bug, bad outcomes)?

- Microbiology

  - Determine the appropriate lab tests to assess relatedness of the organisms from different patients.

    - If, then (prioritize things like mechanism testing and PFGE for different organisms)