CORHA Workgroup B

July Call Notes

7.21.17

- Roll Call – Waleed Javaid, Sri Seshadri, Dawn Terashita, Matt Crist, Steven Franklin, Kate Heyer, Valerie Deloney, Nicole Bryan, Martha Ngoh, Jessica Helms

- Resource Review Form

- Toolkit Element list of the CDC CORHA Prototype Product was combined with the NARR Editorial Review form to build a comprehensive checklist for reviewing resources

- Named fields allow for data extraction (i.e., export to excel)

- Swapped check boxes for page numbers

- Current draft posted to Basecamp

- Scabies subgroup piloting current version/discussing edits on 7/26 call

- Ask WG A for feedback after piloting with multiple diseases

- Need SME input for judging “rating” of documents

  - E.g., look for outdated sections

  - Rating system TBD

- Consider separate document used to combine all review forms per pathogen and add extra sections for SMEs in the consolidated version

- Waleed and Matt to pilot current version with C. diff

- Response Activity Tracking System

- CDC and TN shared tracking systems with each other, Access and REDCap respectively

- Additional data fields have been added

- Highlighted in red considered beneficial to add to database

- Please review data dictionary* on Basecamp and provide feedback to Steven

*CORHA Basecamp -> Docs&Files -> Workgroup B -> Response Activity Tracking System -> CORHA_Sample_Tracking_System_Data Dictionary_HAI-AR_Response_2017_DRAFT_7-20-2017

- Workgroup to review final edits before Aug. 18 call

- Finalize on Aug. 18 call -> Share with full Council one week before ALL CORHA call Aug. 31

- Present on All CORHA Call Aug. 31

- Council will vote via electronic form following call

Action Items

- Scabies group to share final review form edits by Aug. 18 call

- C diff group to pilot with their resources by Aug. 18 call

- Workgroup to send Steven feedback on Response Activity Tracking System by Aug. 4

- Workgroup to review final edits before Aug. 18