CORHA Workgroup Staff Support Needs: Communications

- Identify specific tasks and goals you anticipate needing ASTHO/CSTE staff support to accomplish workgroup deliverables:

  - Develop talking points

  - CORHA website build out of additional pages

  - Website Rollout

  - Participate in workgroup calls

  - Manage dedicated CORHA Email box

  - Maintain subscription list

  - Maintain key partner lists

- Estimate the number of staff hours you expect will be needed to accomplish each of the task(s).

  - Develop talking points (4 hours)

  - CORHA website build out of additional pages (need input from a web developer)

  - Website Rollout (10 hours)

  - Participate in workgroup calls (1 hour a month ongoing)

  - Manage dedicated CORHA Email box (1 hour per week depending on volume ongoing)

  - Maintain subscription list (1 hour per week depending on volume ongoing)

  - Maintain key partner lists (1 hour per week depending on volume ongoing)

- Tasks in progress:

  - Communications Plan – Bonnie

  - Website phase 2 and 3 updates (design and content) - Bonnie

  - Style Guide – Martha

  - Website phase 1 updates - Martha

  - Approval/clearance process - Kate