CORHA Communications and Marketing Taskforce Call

Thursday, December 14 | 12:30 p.m. – 1:30 p.m. ET

Discussion Summary

Michael Anderson, Jeremy Arieh, Stephen Clay, Matt Cone, Bonnie Herring, Kate Heyer, Elizabeth Mothershed, Martha Ngoh, Heidi Satter

- The group received helpful feedback about the CORHA website. Participant feedback included: using relevant images and reformatting the resources table. A report from the focus group activity is attached.

- Website development and refinement (based on focus group feedback) is currently underway. More content copy is required to fully complete the task, which can be accomplished by January 5th.

- There are CORHA products available to post. Michael will work with workgroup B to identify additional resources to post to the website.

- The group is comfortable with the look and feel of the website, but would like to fine-tune additional elements of the website.

- Clay will continue working on publishing the pages he is currently working on, while a contractor will be brought on to bridge the existing website to the final version, within the 45-day timeline.

- Said contractor will work to modify existing pages, develop additional pages and structure the clearinghouse, based on provided storyboards.

Next Steps and Timeline:

| Task | Assignee | Deadline |
| --- | --- | --- |
| Provide requested content for Clay to complete current work underway. | Michael, Martha | Friday, December 22 |
| Discuss resource review process with Workgroup B; Collect identified resources from the workgroup to post to the website. | Michael | TBD (deadline pending WG B discussion on December 15) |
| Create website storyboards using existing mock-pages and other sources. | Heidi, Bonnie, Martha. Final storyboards will be shared with the group for review/high-level awareness. | Wednesday, December 20 |
| Clarify work order details and submit to contractor. | Heidi, Bonnie, Kate, Martha | Friday, December 22 |
| Ongoing communication with contractor to check-in, receive updates and product | Heidi, Bonnie, Martha | Mid-January (Exact date TBD based on discussion with contractor) |