## Fall CORHA Meeting Action Items
Task Name | Primary Assignee | Secondary Assignee | Notes | Column6
Workgroup A
Finalize Outbreak Definitions | Wendy Bamberg | Nicole Bryan
CRE | Maroya Walters | CSTE staff | Share with Governance Committee and present to full Council for a vote.
Baseline | Rachel Stricof
Assessment |  |  | Promote in APIC's e-Newsletter or send email to HAI coordinators to reach Infection Preventionists (staff will draft language)
Draft language for state HAI coordinators to send to IPs, send email to HAI coordinators | Nicole Bryan | Michael Anderson
Discuss promotion of assessment in APIC's e-newsletter - with Linda Greene | CSTE staff
Analyze, write up assessment results | Nicole Bryan
Chapter 4 (high-level guidance) | Rachel Stricof | Nicole Bryan | Get feedback from workgroup A throughout draft process
SHEA representation on WG A | Nicole Bryan |  | Nicole emailed Valerie D. to follow up.
Cross-Cutting – collecting content/resources/abstracts
Develop a written approval process | Kate Heyer |  | Refer to operating guidance
Cross-Cutting – public reporting/consumers | ASTHO Staff
Policy and Legal workgroup |  |  | The workgroup will cover outbreak reporting requirements, consumer and patient notification, and public disclosure and reporting
Workgroup on HAI outbreak disclosure
Cross-Cutting – laboratory-focused | Michael Anderson
Form a workgroup on laboratory practices on HAI outbreak investigation |  |  | Workgroup will function independently of workgroups A and B, but will include workgroups A and B liaisons.
Identify leads
Recruit members, including non-Council members and reps from A and B
Cross-Cutting – Communications and Website
Website completion
Identify upcoming conferences and webinars for CORHA participation
General
List of all current & future products, roles and timelines | All staff
List of commonly used CORHA terminology
Governance Committee/ Staff Debrief
Provide updates on CORHA workgroup activities using charges documents | CSTE staff
Draft letters and scope of work for the laboratory workgroup | Michael Anderson
Draft letters and scope of work for legal/policies reporting workgroup | Martha Ngoh
Refine and manage CORHA roster and membership | ASTHO Staff