## CORHA Activity Tracker
Projects and Activities | Assigned to | Due or End Date | Status | Status Notes
Workgroup A: Detection and Reporting
Finalize Outbreak Definitions | Wendy Bamberg |  | Yellow
SHEA representation on WG A | Michael |  | Green | Task completed
Survey to Public Health | Michael |  | Green | Completed; Analysis in progress
Survey to Healthcare Facilities | Michael |  |  | Letter drafted;
Draft language for state HAI coordinators to send to IPs, send email to HAI coordinators | Michael
Discuss promotion of assessment in APIC's e-newsletter - with Linda Greene | Michael |  |  | Survey announcement included in APIC's 1/25/2018 e-Newsletter; Contact - MaryAlice Lavin
Analyze, write up assessment results | Michael
Table Shell for Reporting Conditions | Michael
Candida auris | Michael |  |  | Final changes and reviews in progress
Clostridium difficile | Michael |  |  | Final changes and reviews in progress
CRE | Michael |  |  | Near-completion
MDRO Gram Negatives | Michael
NTM (extra-pulmonary) | Michael |  |  | Commenced in January
Scabies | Michael |  |  | Finalized; ready for GC and Council vote
Workgroup B: Investigation and Control
Response Activity Tracking System | WG/CORHA Staff |  | Green | Uploaded to the website (on the development site, ready to publish)
Sample Tracking System Data Dictionary | WG/CORHA Staff |  | Green | Uploaded to the website (on the development site, ready to publish)
Candida auris: Investigation Guidance | Michael |  | Yellow | Pending; development phase
Clostridium difficile: Investigation Guidance | Michael |  | Yellow | Pending; development phase
Identifying Top Resources | Michael |  | Yellow
Laboratory Workgroup
Lab workgroup charge | Michael |  | Yellow | Finalized; Will require full Council review
Workgroup member identification and invitation | CORHA Staff |  | Yellow | Draft list of potential WG members available; Leads TBD; Draft invitation packet pending GC review
Policy Workgroup
Policy workgroup charge | ASTHO |  | Yellow | V2 draft pending GC review and discussion
Workgroup member identification and invitation
Resource Reviews
Investigation and Control Resource Reviews | ASTHO | 2017-10-20 | Yellow | In progress; Kate
High-level Guidance |  | 2017-11-30
Product Development | Michael
Chapter 4 | Rachel Stricof |  | Yellow | Ongoing feedback from workgroup A
Chapter 5 | Rachel Stricof |  | Yellow | Edits and changes implemented by Nancy and Rachel. Document should be complete and ready to vote soon.
CORHA In-person Meetings
Spring 2017 In-person Meeting | CSTE | 2017-05-05 | Green | Completed
Fall 2017 In-person Meeting | CSTE | 2017-12-01 | Green | Completed
Spring 2018 in-person Meeting | ASTHO |  | Yellow | Pending meeting date and venue confirmation
All-CORHA Conference Calls
Spring 2017 Conference Call | ASTHO |  | Green | Completed and wrapped up
Fall 2017 Conference Call | ASTHO |  | Green | Completed and wrapped up
Spring 2018 Conference Call | ASTHO |  | Yellow | Canceled due to unmet quorum
Membership and Onboarding
Consumer Rep Engagement and Onboarding |  | 2017-11-08 | Yellow | GC convened call with Lisa McGiffert and others. Next steps to follow.
APHL Engagement | Michael |  | Yellow | APHL accepted CORHA invitation; APHL rep identified (Dr. Jafar Razeq); Onboarding pending
List of Members and Partners (Updates and Maintenance)
All Council member roster | ASTHO |  | Yellow | Available on Basecamp
Workgroup member roster, roles and responsibilities | ASTHO |  | Yellow | Available on Basecamp
Communications and Marketing
CORHA Website | Bonnie/ASTHO
Abstract and resource curation | ASTHO |  |  | Task in progress
Website development | ASTHO |  | Yellow | Phase 1 completed; Phase 2 in progress
Analytics and reports | ASTHO
Other C&M Related Activities | Bonnie/ASTHO
Communication taskforce charge | ASTHO |  |  | Draft shared with group for feedback; also available on Basecamp
CORHA communication plan | ASTHO |  |  | In progress
Infographics and postcards | ASTHO |  |  | Development in progress
Communication activity tracking and sustenance | ASTHO |  |  | Draft shared with group for feedback; also available on Basecamp