## CORHA Activity Tracker
Projects and Deliverables | Assigned to | Due or End Date | Status | Status Notes
Workgroup A: Detection and Reporting
Finalize Outbreak Definitions | Wendy Bamberg |  | Yellow
Survey to Public Health | Michael |  | Green | Completed; Analysis in progress
Survey to Healthcare Facilities | Michael |  |  | Survey letter drafted and sent; Received 76 responses thus far, going to see about another promotional effort via APIC
Discuss promotion of assessment in APIC's e-newsletter - with Linda Greene | Michael |  |  | Blurb on CORHA survey was published in APIC's e-Newsletter
Analyze, write up assessment results | Michael
Table Shell for Reporting Conditions | Michael
Candida auris | Michael |  |  | Final changes and reviews in progress
Clostridium difficile | Michael |  |  | Final changes and reviews in progress
CRE | Michael |  |  | Completed, ready for council review
MDRO Gram Negatives | Michael
NTM (extra-pulmonary) | Michael |  |  | Commenced in January
Scabies | Michael |  |  | Finalized; Posted to the CORHA website.
Workgroup B: Investigation and Control
Response Activity Tracking System | WG/CORHA Staff |  | Green | On the CORHA website
Sample Tracking System Data Dictionary | WG/CORHA Staff |  | Green | On the CORHA website
Candida auris: Investigation Guidance | Michael |  | Yellow | Pending; development phase
Clostridium difficile: Investigation Guidance | Michael |  | Yellow | Pending; development phase
Identifying Top Resources | Michael |  | Yellow
Laboratory Workgroup
Lab workgroup charge | Michael |  | Yellow | Finalized; Will be discussed on the all-CORHA call
Workgroup member identification and invitation | CORHA Staff |  | Yellow | Draft list of potential WG members available; Leads TBD; Draft invitation packet pending GC review
Policy Workgroup
Policy workgroup charge | ASTHO |  | Yellow | V3 of the draft is available on Basecamp and OneDrive for collaborative editing and refinement; Will be presented at the in-person meeting
Workgroup member identification and invitation
Resource Reviews
Investigation and Control Resource Reviews | ASTHO | 2017-10-20 | Yellow | Scabies resources are in progress of being reviewed by CDC SMEs. Review of additional pathogen-specific resources will be forthcoming.
High-Level Guidance |  | 2017-11-30
Product Development Process | ASTHO |  |  | A framework on the development process is currently being drafted
Product Development | Michael
Chapter 4 | Rachel Stricof |  | Yellow | Ongoing feedback from workgroup A
Chapter 5 | Rachel Stricof |  | Yellow | Edits and changes implemented by Nancy and Rachel. Document should be complete and ready for council review.
CORHA In-person Meetings
Spring 2017 In-person Meeting | CSTE | 2017-05-05 | Green | Completed
Fall 2017 In-person Meeting | CSTE | 2017-12-01 | Green | Completed
Spring 2018 in-person Meeting | ASTHO |  | Yellow | Meeting date and venue confirmed; Invitations in progress.
All-CORHA Conference Calls
Spring 2017 Conference Call | ASTHO |  | Green | Completed and wrapped up
Fall 2017 Conference Call | ASTHO |  | Green | Completed and wrapped up
Spring 2018 Conference Call | ASTHO |  | Yellow | Planned for the end of April; Call date and time TBD
Membership and Onboarding
Consumer Rep Engagement and Onboarding |  | 2017-11-08 | Yellow | GC convened call with Lisa McGiffert and others. Next steps to follow.
APHL Engagement | Michael |  | Yellow | APHL accepted CORHA invitation; APHL rep identified (Dr. Jafar Razeq); Onboarding pending
NACCHO Rep | ASTHO |  |  | GC approval of Hillary Hanson's nomination is pending
List of Members and Partners (Updates and Maintenance)
All Council member roster | CORHA Staff |  | Yellow | Available on Basecamp
Workgroup member roster, roles and responsibilities | CORHA Staff |  | Yellow | Available on Basecamp
Communications and Marketing
CORHA Website
CORHA Workgroup to Website Process | ASTHO |  |  | Draft pending GC approval
Abstract and resource curation | ASTHO |  |  | Task in progress; Email to CSTE abtract authors requesting permission to post their resources will be sent by CSTE
Website development | ASTHO |  | Yellow | Website is live; Two CORHA products are available in the "Resource Hub"- ongoing website improvements in progress
Analytics and reports | ASTHO
Other Comm&Mrktg-Related Activities
Communication taskforce charge/activity tracker | ASTHO |  |  | Available on Basecamp
CORHA communication plan | ASTHO |  |  | In progress
Infographics and postcards | ASTHO |  |  | Postcards created. Infographics pending.
| ASTHO |  |  | Available on Basecamp