## CORHA Activity Tracker
Projects and Deliverables | Assigned to | Status (Gr=Completed; Ylw=In Progress; Red=Not Started; Blu=Ongoing) | Notes
Workgroup A: Detection and Reporting
Finalize Outbreak Definitions | Wendy Bamberg | Yellow
Survey to Public Health | Michael | Green | Completed
Analyze, write up assessment results | Michael | Yellow | Analysis in progress
Survey to Healthcare Facilities |  | Green | Survey letter drafted and sent; Received 76 responses thus far, going to see about another promotional effort via APIC
Discuss promotion of assessment in APIC's e-newsletter - with Linda Greene | Michael | Green | Blurb on CORHA survey was published in APIC's e-Newsletter
Analyze, write up assessment results | Michael | Yellow
Table Shell for Reporting Conditions
Candida auris | Michael | Yellow | Final changes and reviews in progress
Clostridium difficile | Michael | Yellow | Final changes and reviews in progress
CRE | Michael | Yellow | Completed, ready for council review
MDRO Gram Negatives | Michael | Red
NTM (extra-pulmonary) | Michael | Yellow | Commenced in January
Scabies | Michael | Green | Finalized; Posted to the CORHA website.
Workgroup B: Investigation and Control
Response Activity Tracking System | WG | Green | On the CORHA Website
Sample Tracking System Data Dictionary | WG | Green | On the CORHA Website
CRE: Investigation Guidance | Michael | Red | Need to initiate work
Candida auris: Investigation Guidance | Michael | Yellow | Pending; development phase
Clostridium difficile: Investigation Guidance | Michael | Yellow | Pending; development phase
Laboratory Workgroup
Lab workgroup charge | Michael | Yellow | Finalized; Will be discussed on the all-CORHA call
Workgroup member identification and invitation | CORHA Staff | Yellow | Onboarding Jafar Razeq in progress
Policy Workgroup
Policy workgroup charge | ASTHO | Yellow | V4 of the draft is available on Basecamp and OneDrive for collaborative editing and refinement; Will be discussed at the in-person meeting
Workgroup member identification and invitation |  | Red
Resource Reviews
Investigation and Control Resource Reviews | ASTHO/Steven F. | Yellow | Scabies resource review in progress. Final review with SMEs scheduled for May 3. Review of CRE resources pending.
High-level Guidance
Development Process | ASTHO | Yellow | HLG proposal pending GC review
Product Development | Michael | Yellow
Chapter 4 |  | Yellow | Ongoing feedback from workgroup A
Chapter 5 |  | Yellow | Edits and changes implemented by Nancy and Rachel. Document should be complete and ready for council review.
CORHA In-person Meetings
Spring 2018 in-person Meeting | ASTHO | Yellow | Invitations issued. Agenda in development/pending GC review
All-CORHA Conference Calls
Spring 2018 Conference Call | ASTHO | Yellow | Conference call with voting members only, scheduled for May 11.
Membership and Onboarding
APHL (Jafar Razeq) | Michael | Yellow | In communication with Jafar Razeq to initiate the on boarding process. A GC member is needed to participate in this on boarding process.
ASTHO (Kris Ehresmann) | ASTHO | Yellow | On boarding Kris Ehresmann in progress
NACCHO (Hillary Hanson) | ASTHO | Red | Hillary Hanson's on boarding process is yet to be initiated
List of Members and Partners (Updates and Maintenance)
All Council member roster | CORHA Staff | Green | Available on Basecamp
Communications and Marketing
CORHA Website
CORHA Workgroup to Website Process | ASTHO | Green
Abstract and resource curation | CORHA Staff | Yellow | In progress; In the process of receiving permission from CSTE abstract authors to post their resources to the CORHA website
Website development | ASTHO | Blue | Ongoing
Analytics and reports | ASTHO | Blue | Ongoing
Other C&M Related Activities
Communication taskforce charge/activity tracker | ASTHO | Green | Available on Basecamp
CORHA communication plan | ASTHO | Green | In progress
Infographics and postcards | ASTHO | Yellow | Postcards available. Infographics pending.