## By project
date | month | event/project due | attended/completed by
create resource list by pathogen/condition (as internal process)
| July | create template | Nicole/Kate
| August | each member completes template | Resource workgroup
| September | compile all completed sections | Nicole/Kate
| September | discuss draft on Council call | ALL
| September | first draft of resource list by pathogen/condition | ALL
| Sept - Nov | email drafts/revisions | Resource workgroup/ALL
| November | final draft completed and sent out to Council | Nicole/Kate
| Nov | CORHA review/approval at in person meeting | Council
Creation of CORHA website (external list of resources by pathogen)
| September | research logo development companies | Nicole
| October | contract with logo development company | Nicole
| December | get initial logo designs | Nicole
| December | work with web developers on layout of web site | Nicole / website workgroup
| February | share desgins with Council for discussion and vote | Council
| February | work with communications/marketing on layout and content of website | Nicole / website workgroup
| March | Finalize logo and vote | Council
| March | web page template/mock up | Nicole
| March | Council approves CORHA logo | Council
| April | Council approves each web page | Council
| June | Final webpage up and running
create toolkit for one condition
| July | form workgroup | Council
| July | choose condition | Toolkit workgroup
| August | environmental scan review | Toolkit workgroup
| August | identify gaps | Toolkit workgroup
| August | outline of toolkit | Toolkit workgroup
| September | assign sections of toolkit | Toolkit workgroup
| Sept-March | write sections | Toolkit workgroup
| April | compile sections | Nicole/Kate
| May | Council review and approve | Council
| June | post on website | Nicole/Kate
calls and meetings
| July | Governance Committee call | Governance Committee
Thursday, August 11 @ 3PM ET | August | Governance Committee call | Governance Committee
Thursday, September 8 @ 3PM ET | September | Governance Committee call | Governance Committee
Thursday, September 15 @ 2-3:30PM ET | September | Council call | Council
Thursday, October 13 @ 3PM ET | October | Governance Committee call | Governance Committee
Thursday, November 10 @ 3PM ET | November | Governance Committee call | Governance Committee
Thurs Nov. 17 and Fri. Nov 18 in DC (ASTHO) | November | Council in-person meeting | Council
Thursday, December 8 @ 3PM ET | December | Governance Committee call | Governance Committee
Thursday, December 15 @ 2-3:30PM ET | December | Council call | Council
Thursday, January 12 @ 3PM ET | January | Governance Committee call | Governance Committee
Thursday, February 9 @ 3PM ET | February | Governance Committee call | Governance Committee
Thursday, March 9 @ 3PM ET | March | Governance Committee call | Governance Committee
| March | Council call | Council
Thursday, April 13 @ 3PM ET | April | Governance Committee call | Governance Committee
Thursday, May 11 @ 3PM ET | May | Governance Committee call | Governance Committee
| May | Council in-person meeting | Council
Thursday, June 8 @ 3PM ET | June | Governance Committee call | Governance Committee
| June | Council call | Council

## By Date
Month | Event/project due | Attended/completed by
July | create template | Nicole/Kate
July | form workgroup | Council
July | choose condition | Toolkit workgroup
July | Governance Committee call | Governance Committee
August | each member completes template | Resource workgroup
August | environmental scan review | Toolkit workgroup
August | identify gaps | Toolkit workgroup
August | outline of toolkit | Toolkit workgroup
August | Governance Committee call | Governance Committee
Sept - Nov | email drafts/revisions | Resource workgroup/ALL
Sept-March | write sections | Toolkit workgroup
September | compile all completed sections | Nicole/Kate
September | discuss draft on Council call | ALL
September | first draft of resource list by pathogen/condition | ALL
September | research logo development companies | Nicole
September | assign sections of toolkit | Toolkit workgroup
September | Governance Committee call | Governance Committee
September | Council call | Council
October | contract with logo development company | Nicole
October | Governance Committee call | Governance Committee
November | final draft completed and sent out to Council | Nicole/Kate
November | Governance Committee call | Governance Committee
November | Council in-person meeting | Council
November | CORHA review/approval at in person meeting | Council
December | get initial logo designs | Nicole
December | work with web developers on layout of web site | Nicole / website workgroup
December | Governance Committee call | Governance Committee
December | Council call | Council
January | Governance Committee call | Governance Committee
February | share desgins with Council for discussion and vote | Council
February | work with communications/marketing on layout and content of website | Nicole / website workgroup
February | Governance Committee call | Governance Committee
March | Finalize logo and vote | Council
March | web page template/mock up | Nicole
March | Governance Committee call | Governance Committee
March | Council call | Council
April | Council approves each web page | Council
April | compile sections | Nicole/Kate
April | Governance Committee call | Governance Committee
May | Council review and approve | Council
May | Governance Committee call | Governance Committee
May | Council in-person meeting | Council
June | Final webpage up and running
June | post on website | Nicole/Kate
June | Governance Committee call | Governance Committee
June | Council call | Council
March | Council approves CORHA logo | Council
create resource list by pathogen/condition (as internal process)
Creation of CORHA website (external list of resources by pathogen)
create toolkit for one condition
calls and meetings | Creation of CORHA website (external list of resources by pathogen)

## Sheet3
| setting | setting | setting | setting
pathogen | resource | resource | n/a | n/a
pathogen | resource | resource | resource | n/a
pathogen | resource | n/a | resource | n/a
pathogen | resource | resource | resource | n/a