## CORHA Activity Tracker
Projects and Deliverables | Responsible Party | Status Notes
Workgroup A: Detection and Reporting
Finalize Outbreak Definitions | Wendy Bamberg | In progress
SHEA representation on WG A | Nicole | Task completed
Survey to Public Health | Nicole | Completed; Analysis in progress
Survey to Healthcare Facilities | Nicole
Draft language for state HAI coordinators to send to IPs, send email to HAI coordinators | Nicole | Letter to HAI Coordinators drafted by staff
Discuss promotion of assessment in APIC's e-newsletter - with Linda Greene | CSTE | Survey announcement included in APIC's 1/25/2018 e-Newsletter; Contact - MaryAlice Lavin
Analyze, write up assessment results | Nicole
Table Shell for Reporting Conditions | Nicole
Candida auris | Nicole
Clostridium difficile | Nicole
CRE | Nicole | Near-completion
MDRO Gram Negatives | Nicole
NTM (extra-pulmonary) | Nicole
Scabies | Nicole
Workgroup B: Investigation and Control
Response Activity Tracking System |  | Approved; Pending website upload
Sample Tracking System Data Dictionary |  | Approved; Pending website upload
Candida auris: Investigation Guidance |  | Pending: Development phase
Clostridium difficile: Investigation Guidance |  | Pending: Development phase
Identifying top resources |  | Pending: Requires staff reviewed resources
Laboratory Workgroup
Lab workgroup charge | Michael | Near-final; Michael integrated feedback from the Governance Committee into the draft; Sent to APHL
Workgroup member identification and invitation | All Staff | List of suggested WG members shared with GC; Leads TBD; Draft invitation letter pending staff review
Policy Workgroup
Policy workgroup charge | ASTHO | Draft pending GC review and feedback
Workgroup member identification and invitation
Resource Reviews
Investigation and Control Resource Reviews | Michael | Pending: being conducted by CORHA staff
High-level Guidance
Product Development | Nicole
Chapter 4 | Rachel Stricof | Ongoing feedback from workgroup A
Chapter 5 | Rachel Stricof | Being edited by Nancy Maddox
CORHA In-person Meetings
Spring 2017 In-person Meeting | CSTE | Completed and wrapped up
Fall 2017 In-person Meeting | CSTE | Completed and wrapped up
Spring 2018 in-person Meeting | ASTHO | Pending meeting date and venue confirmation
All-CORHA Conference Calls
Spring 2017 Conference Call | ASTHO | Completed and wrapped up
Fall 2017 Conference Call | ASTHO | Completed and wrapped up
Spring 2018 Conference Call | ASTHO | Agenda finalized; pending full council distribution
Membership and Onboarding
Consumer Rep Engagement and Onboarding |  | GC convened call with Lisa McGiffert and others. Next steps to follow
APHL Engagement | Michael | Sent APHl letter on 1/30/2018; APHL accepted letter to the Council. Next steps to follow
List of Members and Partners (Updates and Maintenance)
All Council member roster | ASTHO | Available on Basecamp
Workgroup member roster, roles and responsibilities | CSTE
Communications and Marketing
CORHA Website
Website development | ASTHO | Phase 1 completed; Phase 2 underway
Promotional activities | Comm taskforce | Activities to increase awareness on CORHA are underway

## Meetings and Conferences
CORHA-Related Conferences and Meetings
Meeting/Conference | Date | Location | GC/CORHA Rep | Contact Person/Org | Email | Notes/Action Taken | Rep Needs
APHL | 2018-01-31 | Remote participation | Joe Perz; Michael and Kate | Kevin Bradley/APHL | kevin.bradley@aphl.org | Joe to present on CORHA and introduce APHL members to CORHA and lab engagement | CORHA PowerPoint Slides
CSTE annual conference | June 10-14 | West Palm Beach, FL | All GC members and staff | CSTE staff |  | Several abstracts submitted | PPT slides, marketing materials
APIC annual conference | June 13-15 | Minneapolis, MN | Joe Perz, Linda Greene |  |  | Abstract submitted | PPT slides, marketing materials
SHEA | April 8-10 | Portalnd, OR | Joe Perz |  |  | Joe to present | PPT slides, marketing materials
2018 CORHA Conference Calls and Meetings
Meeting/Call | Month | Format | Host | Location
All-CORHA Call | February | Teleconference Call | ASTHO
Spring In-person Meeting | May | In-person Meeting | ASTHO | Atlanta, GA
All-CORHA Call | June | Teleconference Call | ASTHO
All-CORHA Call | August | Teleconference Call | ASTHO
Fall In-person Meeting | October | In-person Meeting | CSTE | Atlanta, GA
All-CORHA Call | December | Teleconference Call | ASTHO