## Sheet1
ICD-10-CM Drug Poisoning Indicator Programming Subworkgroup | [6 empty] | Fall 2017
Select a period to highlight at right. A legend describing the charting follows. | [6 empty] | Day Highlight: | 2017-10-12 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Project Coordinator: |  | Cody Custis, Katelyn Hall, and Fan Xiong
Project Analyst: |  | Cody Custis, Katelyn Hall, and Fan Xiong
ACTIVITY | Notes | TEAM MEMBER(s) | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Days
[8 empty] | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat
 | time axis 2017-09-20 to 2018-04-07
Kickoff Meeting | Plan out project | All Members of CSTE Drug Poisoning Indicators Workgroup | 2017-09-20 | 2 | 2017-09-20 | 2 | 100%
Write out program logic | In our working draft of code, comment out the logic to complete the 7 analyses for helping determine the final case definition. | Programming Sub-workgroup: Cody, Katelyn, Fan | 2017-10-01 | 15 | 2017-10-01 | 5 | 70%
Write SAS code functions | Add code functions to the commented draft, run tests on the functions | Programming Sub-workgroup: Cody, Katelyn, Fan | 2017-10-08 | 8 | 2017-10-01 | 8 | 70%
Send working code to the programming group for feedback | Have code as final and tested as possible using CO, MT, and KS data. Send final cleaned up code to interal programming group for feedback. | Programming Sub-workgroup | 2017-10-18 | 2 | 2017-10-18 | 8 | 100%
Receive all feedback from internal group (Send to Cody) | Programming group will provide feedback from the code sent out on the 18th | Programming Sub-workgroup | 2017-10-30 | 2 | 2017-10-18 | 8 | 0%
Run SAS program on validation dataset | Run finalized SAS program on the validation data for confirmation that the code counts the 7 analyses appropriately. | Programming Sub-workgroup and Validation Dataset Sub-workgroup | 2017-10-30 | 10 |  | 10 | 0%
Send validated code back to programming sub-workgroup | All states run the validated code on their datasets and provide back results for the 7 analyses. | Programming Sub-workgroup | 2017-11-13 | 11 |  | 11 | 0%
Final Code | Update code based on any feedback from programming sub-workgroup | Programming Sub-workgroup | 2017-11-28 | 11 |  | 11 | 0%
Provide final moc up results to excel sub-workgroup | Update code based on any feedback from programming sub-workgroup | Programming Sub-workgroup and Excel Sub-workgroup | 2017-11-28 | 11 |  | 11 | 0%
All results in excel | All jurisdictions have results completed in excel and sent to the Workgroup | Programming Sub-workgroup and ICD-10-CM Drug Poisoning Workgroup | 2017-12-13 | 1 |  | 1 | 0%
Projected Completion | [6 empty] | 34%
Formulas:
PLAN START = WORKDAY([PLAN START, row above],[ACTUAL DURATION, row above])