## Project Timeline
CSTE ICD-10-CM Drug Poisoning Indicators Workgroup: Programming Sub-workgroup
TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE | Position Adjusted | Date adjusted | Milestone adjusted
2017-09-21 | Kick Off Meeting | 25 | 0 | 25 | 2017-09-21 | Kick Off Meeting
2017-10-01 | Code Logic | 10 | 0 | 10 | 2017-10-01 | Code Logic
2017-10-08 | Code Functions | -10 | 0 | -10 | 2017-10-08 | Code Functions
2017-10-20 | Feedback from Programming Group | 15 | 0 | 15 | 2017-10-20 | Feedback from Programming Group
2017-11-06 | Run Program on Validation Data | -15 | 0 | -15 | 2017-11-06 | Run Program on Validation Data
2017-11-20 | Jurisdictions Test Run Code | 10 | 0 | 10 | 2017-11-20 | Jurisdictions Test Run Code
2017-12-05 | Complete Working Code | -15 | 0 | 15 | 2017-12-05 | Provide Moc Up Result to Excel Team
2017-12-05 | Provide Moc Up Result to Excel Team | 15 | 0 | -15 | 2017-12-05 | Complete Working Code
2017-12-20 | All Juridictions Have Results in Excel | -20 | 0 | -20 | 2017-12-20 | All Juridictions Have Results in Excel
| Milestone 9 | 20 |  | 5 | 2017-12-31
| Milestone 10 | -15 |  | 5 | 2017-12-31
| Project End | 15 |  | 5 | 2017-12-31
Formulas:
DATE = [DATE, row above]+10
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.

## Project Data Sorted (hidden)
Sort the dates to populate the timeline in chronological order
|  |  | data analysis | [5 empty] | Actual data to chart, which is fed into the Project Timeline worksheet via hidden columns F-H.
| start row | 20 | TIE BREAK | RANK | DATE | MILESTONE | POSITION | NUM | RANK Sorted | DATE | MILESTONE | POSITION
| last entry | 28 | 9 | 1 | 2017-09-21 | Kick Off Meeting | 25 | 8 | 9 | 2017-09-21 | Kick Off Meeting | 25
|  |  | 8 | 2 | 2017-10-01 | Code Logic | 10 | 7 | 8 | 2017-10-01 | Code Logic | 10
|  |  | 7 | 3 | 2017-10-08 | Code Functions | -10 | 6 | 7 | 2017-10-08 | Code Functions | -10
|  |  | 6 | 4 | 2017-10-20 | Feedback from Programming Group | 15 | 5 | 6 | 2017-10-20 | Feedback from Programming Group | 15
|  |  | 5 | 5 | 2017-11-06 | Run Program on Validation Data | -15 | 4 | 5 | 2017-11-06 | Run Program on Validation Data | -15
|  |  | 4 | 6 | 2017-11-20 | Jurisdictions Test Run Code | 10 | 3 | 4 | 2017-11-20 | Jurisdictions Test Run Code | 10
|  |  | 2 | 7 | 2017-12-05 | Complete Working Code | -15 | 2 | 3 | 2017-12-05 | Provide Moc Up Result to Excel Team | 15
|  |  | 3 | 7 | 2017-12-05 | Provide Moc Up Result to Excel Team | 15 | 1 | 2 | 2017-12-05 | Complete Working Code | -15
|  |  | 1 | 9 | 2017-12-20 | All Juridictions Have Results in Excel | -20 | 0 | 1 | 2017-12-20 | All Juridictions Have Results in Excel | -20