## Project Timeline
PHASE II PROJECT TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE | Position Adjusted | Date adjusted | Milestone adjusted
2018-02-05 | Project Start | 25 | 0 | 25 | 2018-02-05 | Project Start
2018-02-08 | Meet for Phase II Planning | 10 | 0 | 10 | 2018-02-08 | Meet for Phase II Planning
2018-02-28 | MT and CO Test Code | -10 | 0 | -10 | 2018-02-28 | MT and CO Test Code
2018-03-03 | Develop excel output | 15 | 0 | 15 | 2018-03-03 | Develop excel output
2018-03-05 | Finalize Phase II Code | -15 | 0 | -15 | 2018-03-05 | Finalize Phase II Code
2018-03-09 | Validate Phase II Code | 15 | 0 | 15 | 2018-03-09 | Validate Phase II Code
2018-03-12 | Send out final phase II code for Jurisdictions that submitted before | -15 | 0 | -15 | 2018-03-12 | Send out final phase II code for Jurisdictions that submitted before
2018-03-19 | Send out Phase II Code to all Jurisdictions | 15 | 0 | 15 | 2018-03-19 | Send out Phase II Code to all Jurisdictions
2018-04-06 | All Jurisdictions Submit Excel Sheets to Hal | -20 | 0 | -20 | 2018-04-06 | All Jurisdictions Submit Excel Sheets to Hal
2018-05-03 | Present Phase II Findings | 20 | 0 | 20 | 2018-05-03 | Present Phase II Findings

## Project Data Sorted (hidden)
Sort the dates to populate the timeline in chronological order
|  |  | data analysis | [5 empty] | Actual data to chart, which is fed into the Project Timeline worksheet via hidden columns F-H.
| start row | 5 | TIE BREAK | RANK | DATE | MILESTONE | POSITION | NUM | RANK Sorted | DATE | MILESTONE | POSITION
| last entry | 14 | 10 | 1 | 2018-02-05 | Project Start | 25 | 9 | 10 | 2018-02-05 | Project Start | 25
|  |  | 9 | 2 | 2018-02-08 | Meet for Phase II Planning | 10 | 8 | 9 | 2018-02-08 | Meet for Phase II Planning | 10
|  |  | 8 | 3 | 2018-02-28 | MT and CO Test Code | -10 | 7 | 8 | 2018-02-28 | MT and CO Test Code | -10
|  |  | 7 | 4 | 2018-03-03 | Develop excel output | 15 | 6 | 7 | 2018-03-03 | Develop excel output | 15
|  |  | 6 | 5 | 2018-03-05 | Finalize Phase II Code | -15 | 5 | 6 | 2018-03-05 | Finalize Phase II Code | -15
|  |  | 5 | 6 | 2018-03-09 | Validate Phase II Code | 15 | 4 | 5 | 2018-03-09 | Validate Phase II Code | 15
|  |  | 4 | 7 | 2018-03-12 | Send out final phase II code for Jurisdictions that submitted before | -15 | 3 | 4 | 2018-03-12 | Send out final phase II code for Jurisdictions that submitted before | -15
|  |  | 3 | 8 | 2018-03-19 | Send out Phase II Code to all Jurisdictions | 15 | 2 | 3 | 2018-03-19 | Send out Phase II Code to all Jurisdictions | 15
|  |  | 2 | 9 | 2018-04-06 | All Jurisdictions Submit Excel Sheets to Hal | -20 | 1 | 2 | 2018-04-06 | All Jurisdictions Submit Excel Sheets to Hal | -20
|  |  | 1 | 10 | 2018-05-03 | Present Phase II Findings | 20 | 0 | 1 | 2018-05-03 | Present Phase II Findings | 20