Phase III meeting 7-5-2018

Participants: Cody Custis and Katelyn Hall

-polydrug and ED visit coding

What polydrugs?

Two approaches:

- Those of interest eg benzos and opiates, because jurisdictions have an interest, those that are severe

- Data driven approach-not sure how useful

  - Will try this on a very simple level

    - Pull all drug codes for each case

    - Label into higher chapters

    - Cross-tab those chapters

Talk with Jim D. and get a list, that should cover 90%

NOTE: Not going to include alcohol in polydrug-so major limitation

NOTE: Phase IV - case definition for drugs with the potential for abuse

Tables:

- Predetermined drug combos

- Data driven drug combos

  - Drug pairs vs polydrug (3 or more drugs)

    - Do a crosstab of those with Pairs, and those with pairs and polydrug

      - Run this in CO and MT and see if it is worth two tables

Start here, see what we have and talk to subject matter experts to maybe look at specific outcomes

- We may want to look at discharge status for polydrug

For ED, run all tables on CO and MT and then select the useful the tables to present to the larger group

Timeline:

-Meet with Jim next week July 9-13

-Cody drafts code to have preliminary by Aug 23

-CO/MT does preliminary tables by Aug 3

-Start ED code mid August

Next steps:

Cody schedule call with Jim

Katelyn next steps create timeline