## Project Timeline
PHASE III PROJECT TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE | Position Adjusted | Date adjusted | Milestone adjusted
2018-07-06 | Planning Meeting 1 | 20 | 0 | 20 | 2018-07-06 | Planning Meeting 1
2018-07-12 | Planning Meeting 2 | -10 | 0 | -10 | 2018-07-12 | Planning Meeting 2
2018-07-23 | Preliminary Code Sent to CO/MT | 15 | 0 | -10 | 2018-07-12 | Planning Meeting 2
2018-08-03 | CO/MT Provide results from preliminary code | -15 | 0 | 15 | 2018-07-23 | Preliminary Code Sent to CO/MT
2018-08-15 | Finalize code | -15 | 0 | -15 | 2018-08-03 | CO/MT Provide results from preliminary code
2018-08-20 | Send Out Final Code to States | 20 | 0 | -15 | 2018-08-15 | Finalize code
2018-09-06 | Workgroup Meeting-share updates and troubleshoot | 10 | 0 | 20 | 2018-08-20 | Send Out Final Code to States
2018-09-15 | Receive Final Tables | 20 | 0 | 20 | 2018-08-20 | Send Out Final Code to States
|  |  |  | 20 | 2018-09-15 | Receive Final Tables

## Project Data Sorted (hidden)
Sort the dates to populate the timeline in chronological order
|  |  | data analysis | [5 empty] | Actual data to chart, which is fed into the Project Timeline worksheet via hidden columns F-H.
| start row | 5 | TIE BREAK | RANK | DATE | MILESTONE | POSITION | NUM | RANK Sorted | DATE | MILESTONE | POSITION
| last entry | 12 | 8 | 1 | 2018-07-06 | Planning Meeting 1 | 20 | 7 | 8 | 2018-07-06 | Planning Meeting 1 | 20
|  |  | 7 | 2 | 2018-07-12 | Planning Meeting 2 | -10 | 6 | 7 | 2018-07-12 | Planning Meeting 2 | -10
|  |  | 6 | 3 | 2018-07-23 | Preliminary Code Sent to CO/MT | 15 | 5 | 6 | 2018-07-23 | Preliminary Code Sent to CO/MT | 15
|  |  | 5 | 4 | 2018-08-03 | CO/MT Provide results from preliminary code | -15 | 4 | 5 | 2018-08-03 | CO/MT Provide results from preliminary code | -15
|  |  | 4 | 5 | 2018-08-15 | Finalize code | -15 | 3 | 4 | 2018-08-15 | Finalize code | -15
|  |  | 3 | 6 | 2018-08-20 | Send Out Final Code to States | 20 | 2 | 3 | 2018-08-20 | Send Out Final Code to States | 20
|  |  | 2 | 7 | 2018-09-06 | Workgroup Meeting-share updates and troubleshoot | 10 | 1 | 2 | 2018-09-06 | Workgroup Meeting-share updates and troubleshoot | 10
|  |  | 1 | 8 | 2018-09-15 | Receive Final Tables | 20 | 0 | 1 | 2018-09-15 | Receive Final Tables | 20