## Project Timeline
PHASE IV: ED Discharges PROJECT TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE | Position Adjusted | Date adjusted | Milestone adjusted
2018-11-01 | Planning Meeting 1 | 20 | 0 | 20 | 2018-11-01 | Planning Meeting 1
2018-11-15 | Phase IV Code Draft | -10 | 0 | -10 | 2018-11-15 | Phase IV Code Draft
2018-11-30 | Run Phase IV Code in CO/MT | 15 | 0 | -10 | 2018-11-15 | Phase IV Code Draft
2018-12-07 | Finalize Code Sent to States | -15 | 0 | 15 | 2018-11-30 | Run Phase IV Code in CO/MT
2019-01-07 | States Results Due | -15 | 0 | -15 | 2018-12-07 | Finalize Code Sent to States
2019-01-15 | Present in Atlanta Meeting | 20 | 0 | -15 | 2019-01-07 | States Results Due
|  |  |  | 20 | 2019-01-15 | Present in Atlanta Meeting
|  |  |  | 20 | 2019-01-15 | Present in Atlanta Meeting
|  |  |  | 5 | #NAME?

## Project Data Sorted (hidden)
Sort the dates to populate the timeline in chronological order
|  |  | data analysis | [5 empty] | Actual data to chart, which is fed into the Project Timeline worksheet via hidden columns F-H.
| start row | 5 | TIE BREAK | RANK | DATE | MILESTONE | POSITION | NUM | RANK Sorted | DATE | MILESTONE | POSITION
| last entry | 10 | 6 | 1 | 2018-11-01 | Planning Meeting 1 | 20 | 5 | 6 | 2018-11-01 | Planning Meeting 1 | 20
|  |  | 5 | 2 | 2018-11-15 | Phase IV Code Draft | -10 | 4 | 5 | 2018-11-15 | Phase IV Code Draft | -10
|  |  | 4 | 3 | 2018-11-30 | Run Phase IV Code in CO/MT | 15 | 3 | 4 | 2018-11-30 | Run Phase IV Code in CO/MT | 15
|  |  | 3 | 4 | 2018-12-07 | Finalize Code Sent to States | -15 | 2 | 3 | 2018-12-07 | Finalize Code Sent to States | -15
|  |  | 2 | 5 | 2019-01-07 | States Results Due | -15 | 1 | 2 | 2019-01-07 | States Results Due | -15
|  |  | 1 | 6 | 2019-01-15 | Present in Atlanta Meeting | 20 | 0 | 1 | 2019-01-15 | Present in Atlanta Meeting | 20