## Timeline
TIMELINE TEMPLATES by Vertex42.com
https://www.vertex42.com/ExcelTemplates/timeline.html
Tips for Using this Template
• Insert and delete entire rows when editing the data tables
• Avoid leaving the label column blank
• Format the horizontal axis to set min/max bounds
• Enter a vertical position between -100 and 50
• Format individual data labels or markers to highlight specific events
• Read cell comments in the table header row for more information
Other Notes
• Milestone leader lines are Y Error bars
• Task leader lines are Y Error bars
• Task durations are X Error bars
Tasks
Start | End | Duration | Label | Vert. Position | Vert. Line
2019-03-07 | 2019-03-07 | 1 | Present Phase VI Results | -15 | -15
2019-03-08 | 2019-03-15 | 8 | Recruit Phase V members | -25 | -10
2019-03-16 | 2019-03-18 | 3 | Deligate | -35 | -10
2019-03-19 | 2019-03-31 | 13 | Production Time | -45 | -10
2019-04-01 | 2019-04-03 | 3 | Share/edit Drafts | -55 | -10
2019-04-04 | 2019-04-15 | 12 | Larger WG Edits Drafts | -65 | -10
2019-04-16 | 2019-04-30 | 15 | Finalize Drafts | -75 | -10
2019-05-01 | 2019-05-01 | 1 | Share Final Drafts with Larger WG | -85 | -10
2019-05-01 | 2019-05-15 | 15 | Submission Phase | -15 | -15
Insert new rows above this one
Milestones
Date |  |  | Label | Position
2019-03-08 |  |  | Start Phase V | 10
2019-03-18 |  |  | WG Meeting | 15
2019-04-01 |  |  | WG Meeting | 10
2019-04-04 |  |  | ICD-10-CM Drug Posioning WG Call | 30
2019-04-08 |  |  | WG Meeting | 15
2019-04-29 |  |  | WG Meeting | 15
2019-05-02 |  |  | ICD-10-CM Drug Posioning WG Call | 30
2019-05-15 |  |  | Finish Phase V | 10
Insert new rows above this one
Formulas:
End = [Start]+[Duration]-1
Start = [End, row above]+1
Note on A29: Start Date: You can manually enter the Start Date, or you can use a formula to start a task the day after the completion of a previous task such as =end_date+1
Note on B29: End Date: You can manually enter the End Date, or you can calculate the End Date from the Start Date and Duration using the formula =start_date+duration-1.
Note on C29: Task Duration: To show the duration of a task as a horizontal bar, enter the number of days in this column. Leave the column blank if you do not want to display durations. If you enter the End Date, you can calculate the Duration using the formula =end_date-start_date+1.
Note on D29: Labels: The data labels used in the chart refer to this column. Text wrapping within data labels is difficult to control, but you can force a new line within the text by pressing Alt+Enter while typing in a cell to enter a carriage return.
Note on E29: Vertical Position: Edit the vertical position of each task to avoid overlap. To use a different vertical scale, format the vertical axis to adjust the Minimum and Maximum bounds.
Note on F29: Vertical Line: Defines the length of the vertical leader line for each task. To extend the leader line all the way to the horizontal axis, set the vertical line length equal to the vertical position. To extend the leader line to the previous task, set the vertical line length equal to the vertical position minus the vertical position of the previous task.

## About
PROJECT TIMELINE by Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-timeline.html
About This Template
This template uses a scatter chart with data labels and error bars to create a project timeline that shows both milestones and tasks with durations. Unlike a Gantt chart, which shows each task on a separate row, you control the vertical positioning of tasks within the timeline. You can specify the length of the vertical leader line to help show task dependencies.
This type of project timeline is mainly useful for a general overview of a project rather than showing a detailed work breakdown structure.
More Templates
Visit Vertex42.com to download other timeline and project management templates.
More Timeline Templates
More Project Management Templates
About Vertex42
Vertex42.com provides professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.