|  | Build Knowledge | Build Knowledge | Build Knowledge | Translating Data | Translating Data |
| --- | --- | --- | --- | --- | --- |
| Work Product | Inventory Pollen Station Data - Resource | Determine the spatial representation of a sensor | Refine definition(s) of ESSENCE query | Communications Tool kit | Intentional Collaborations |
| Work Plan | - Share EPHT Pollen Sub-team document with CSTE group (Emily and Allison 5/14/2019) - Share Resource Guide to Google Docs (Allison) - Short presentation by EPHT Sub-team (next CSTE aeroallergen) - Members add pollen station data | - Send Emory proposal to CSTE Aeroallergen WG members (Arie) - Updates of project (Ongoing - Yiu) - Develop case study of Yui (4/1/2020) | - Develop ESSENCE query (Mike Coletta, Shubhayu) - Define sensitive populations (Eyal Oren) - Online Demo of ESSENCE (7/30/2019) | - Create Shared Slideset (Office, Outlook) (Arie 5/15/2019) - Members add their slides (7/1/2019) - Revisiting draft slide deck; how do we want it structured | - NADP Collaborations (Andy 5/14/2019) - Medical Consortium on Climate Change (Allison 5/14/2019) - Seek feedback from Medical Consortium on Climate Change on ESSENCE - NAACP collaborations (Allison 5/14/2019) - Connect with EPA aeroallergens collaborators (Arie seek collaborations with EPA 5/21/2019) |
| Win | - Comprehensive list of pollen counting stations, including NAB data and non-NAB data - National map of locations collecting pollen data - Available to Workgroup members | - Determine the distance that one pollen counting station represents - Determine the temporal resolution of - Pollen variation in space and time | - Patients use alerting (based on Essence and pollen data) to help manage their allergies - Physicians have better knowledge on how pollen affects health, and the contribution of climate factors to timing. | - Slide Deck that explains other projects (e.g. Develop a How-to-Guide similar to Wildfires from Washington State) - Refine an Elevator Speech - Identify and reach out to vulnerable Populations - Toolkit guidance document | - Collaborate with key players for aeroallergen messaging |