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	Work Product
	Inventory Pollen Station Data - Resource
	Determine the spatial representation of a sensor 
	Refine definition(s) of ESSENCE query
	Communications Tool kit
	Intentional Collaborations

	Work Plan
	· Share EPHT Pollen Sub-team document  with CSTE group (Emily and Allison 5/14/2019)
· Share Resource Guide to Google Docs (Allison)
· Short presentation by EPHT Sub-team (next CSTE aeroallergen)
· Members add pollen station data
	· Send Emory proposal to CSTE Aeroallergen WG members (Arie)
· Updates of project (Ongoing - Yiu)
· Develop case study of Yui (4/1/2020)
	· Develop ESSENCE query (Mike Coletta, Shubhayu)
· Define sensitive populations (Eyal Oren)
· Online Demo of ESSENCE (7/30/2019)
	· Create Shared Slideset (Office, Outlook) (Arie 5/15/2019)
· Members add their slides (7/1/2019)
· Revisiting draft slide deck; how do we want it structured

	· NADP Collaborations (Andy 5/14/2019)
· Medical Consortium on Climate Change (Allison 5/14/2019)
· Seek feedback from Medical Consortium on Climate Change on ESSENCE
· NAACP collaborations (Allison 5/14/2019)
· Connect with EPA aeroallergens collaborators (Arie seek collaborations with EPA 5/21/2019)

	Win
	· Comprehensive list of pollen counting stations, including NAB data and non-NAB data
· National map of locations collecting pollen data
· Available to Workgroup members
	· Determine the distance that one pollen counting station represents
· Determine the temporal resolution of 
· Pollen variation in space and time
	· Patients use alerting (based on Essence and pollen data) to help manage their allergies
· Physicians have better knowledge on how pollen affects health, and the contribution of climate factors to timing.
	· Slide Deck that explains other projects (e.g. Develop a How-to-Guide similar to Wildfires from Washington State)
· Refine an Elevator Speech
· Identify and reach out to vulnerable Populations
· [bookmark: _GoBack]Toolkit guidance document
	· Collaborate with key players for aeroallergen messaging



