# Biweekly Status Report to Workgroup

| Project: | CSTE Data Standardization Workgroup |
| --- | --- |

| To: | Shaily Krishan, Meredith Lichtenstein, Shannon Harney, and Molly Crockett |
| --- | --- |
| CC: | Workgroup Members |
| From: | Emily Augustini and Elizabeth Sprouse |
| Date: | 5-4-18 |

# Overall Status for May 4, 2018

| Status | Comments |
| --- | --- |
| On Track | After the slight slowdown due to the extended discussion of Date of Illness Onset, the co-chairs, JMC and CSTE have adjusted our plan to allow for a thorough consensus process. Though it means we may complete fewer variables, this will ensure the processes are sustainable and effective. |

# Activities Performed and Accomplishments This Period

The CSTE Data Standardization Workgroup has convened one time this reporting period, during which discussion of proposed solutions for the Date of Illness Onset was completed, and initial input was garnered for Diagnosis Date. Below is a summary of the dialogue and proposed solutions from this meeting:

- We discussed the remaining types of variation in Date of Illness Onset usage, which included:

  - Reconciling conflicting dates from different sources

  - Which signs and symptoms should be used (any sign, only those in the case definition, or a defining symptom)

- Solutions for these sources of variation were suggested. These are listed below and were included in the proposed definition distributed this week.

  - The patient remains the source of “truth.” If there are conflicting dates between sources, the patient/proxy information should be prioritized (assuming the patient is reliable).

  - Relevant signs and symptoms used to determine Date of Illness Onset will vary by condition. In general, we recommend that the earliest sign or symptom should be used, with deference to the existing disease-specific guidance.

- Workgroup members shared their experiences using Diagnosis Date. A summary of different usages of the variable is below:

  - Diagnosis Date is a calculated field that is always populated, using either clinical or laboratory data, and used as a key date in the system.

    - For asymptomatic diseases, such as TB, Diagnosis Date can be more useful during investigation than Date of Illness Onset.

  - Diagnosis Date feeds into the Event Date algorithm, but is not used often alone.

# Status of Data Elements under Discussion

| Data Element | Solicit Initial Input | Discussion on Workgroup Call | Distribute Sample Definitions | Vote on Definitions | Discuss Results on Workgroup Call | Develop Consensus Definition | Present Definition to CSTE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date of Illness Onset | √ | √ | √ |  |  |  |  |
| Diagnosis Date | √ | √ |  |  |  |  |  |
| Date First Reported to PHD |  |  |  |  |  |  |  |

# Activities Planned For The Next Reporting Period

- Long-term roadmap assessment: Members will be assisting in the planning for Workgroup activities following the 2018 CSTE Annual Conference using an online survey. We have drafted survey questions and will solicit feedback from Workgroup members after the consensus definition for Date of Illness Onset is finalized. This will allow members to comment on the consensus process.

- Consensus vote for Date of Illness Onset: The initial discussion of Date of Illness Onset had been completed and the draft definition has been distributed. Members are reviewing and providing their feedback on the definition.

- Diagnosis Date discussion: We have begun the initial discussion of Diagnosis Date by gathering input from different jurisdictions. In the coming weeks, we will seek solutions for common discrepancies in the usage of this variable.