# Biweekly Status Report to Workgroup

| Project: | CSTE Data Standardization Workgroup |
| --- | --- |

| To: | Shaily Krishan, Meredith Lichtenstein, Shannon Harney, and Molly Crockett |
| --- | --- |
| CC: | Workgroup Members |
| From: | Emily Augustini and Elizabeth Sprouse |
| Date: | 5-18-18 |

# Overall Status for May 18, 2018

| Status | Comments |
| --- | --- |
| On Track | On track according to adjusted timeline after the extended Date of Illness Onset discussion |

# Activities Performed and Accomplishments This Period

The CSTE Data Standardization Workgroup has convened one time this reporting period, which consisted of an extensive discussion of potential sources of variation in Diagnosis Date variable usage. Below is a summary of the sources of variation and other input from this meeting:

- Source of information

  - Workgroup members use both clinical and laboratory information to determine Diagnosis Date, not necessarily in a defined hierarchy

  - Most members would not use patient self-reported date of physician diagnosis

- Meaning of “diagnosis”

  - There are two methods of defining Diagnosis Date: when the condition was first suspected or when conclusive evidence of diagnosis was available

    - For example, when a physician first noted symptoms potentially indicating a disease, versus a conclusive lab result or report to public health

  - The method used varies depending on the jurisdiction, condition, available information and surveillance system needs

- Dates most commonly used

  - Members most often use Specimen Collection Date, Lab Result Date, and Date Reported to Public Health

  - Specimen Collection date is used very often because it is generally available

# Status of Data Elements under Discussion

| Data Element | Solicit Initial Input | Discussion on Workgroup Call | Distribute Sample Definitions | Vote on Definitions | Discuss Results on Workgroup Call | Develop Consensus Definition | Present Definition to CSTE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date of Illness Onset | √ | √ | √ |  |  |  |  |
| Diagnosis Date | √ | √ |  |  |  |  |  |
| Date First Reported to PHD |  |  |  |  |  |  |  |

# Activities Planned For The Next Reporting Period

- Long-term roadmap assessment: Members will be assisting in the planning for Workgroup activities following the 2018 CSTE Annual Conference using an online survey. We are finalizing the questions for the survey and plan to distribute to workgroup members in the coming week.

- Consensus vote for Date of Illness Onset: The initial discussion of Date of Illness Onset has been completed and the draft definition has been distributed. Members are still able to review and provide their feedback on the definition, and a revised definition will be presented on the next workgroup call.

- Diagnosis Date discussion: We will finish gathering initial input on Diagnosis Date usage and begin to discuss proposed solutions to the sources of variation.